## 2019-Summer
2019-02-06
LCCMR November 2018 - January 2020 Calendar (Annual Funding Cycle) Adopted 11/13/2018
(20 meetings = 28 days)
Mtg # | # Days | Date | Subject
1 | 1 | November 13, 2018 (Tues.) | LCCMR Meeting: Review language for 2019 recommendations; report back on completed projects; peer review results for 2019 recommendations; discuss/adopt Biennial Report; review 2013-2019 Strategic Plan; discuss 2020 RFP, including evaluation criteria; discuss strategic planning for 2019
2 | 1 | December 4, 2018 (Tues.) | LCCMR Meeting: Adopt language for 2019 recommendations; adopt strategic plan; adopt 2020 RFP; finalize strategic planning 2019; adopt 2019 calendar
|  | December 12, 2018 (Wed.) | LCCMR Meeting (if needed): Finalize 2020 RFP CANCELED
Issue 2020 Request for Proposal (RFP); January 2019
3 | 1 | January/February xx, 2019 | Optional Meeting as Needed
2019 Legislative Session begins January 8, 2019 (Tues.)
Draft proposals due in response to 2019 Request for Proposal: March 15, 2019 (Friday)
Proposals due in response to 2020 Request for Proposal: April 15, 2019 (Monday)
Last Day of 2019 Legislative Session: May 20, 2019 (Mon.)
Commission Members receive proposal books to review and evaluate: Mid May 2019
4 | 2 | June 5 & 6, 2019 (Wed. & Thurs.) | LCCMR Meeting - Discuss 2020 proposals received; select 2020 proposals to call in for presentation; biennial report; session review; approve 2019 work plans; other business, and LCCMR Local Site Visit
5 | 1 | June 17, 2019 (Mon.) | LCCMR Meeting: 2020 Proposal Presentations
6 | 1 | June 18, 2019 (Tues.) | LCCMR Meeting: 2020 Proposal Presentations
7 | 1 | June 24, 2019 (Mon.) | LCCMR Meeting: 2020 Proposal Presentations
8 | 1 | June 25, 2019 (Tues.) | LCCMR Meeting: 2020 Proposal Presentations
9 | 1 | June 26, 2019 (Wed.) | LCCMR Meeting: 2020 Proposal Presentations
10 | 1 | June 27, 2019 (Thurs.) | LCCMR Meeting: 2020 Proposal Presentations
11 | 2 | July 17-18, 2019 (Wed. - Thurs.) | LCCMR Meeting: 2020 Allocation discussion and decisions
Peer Review/ Technical Review August-November
Project Managers Prepare Work Plans August-September
12 | 3 | August 13, 14, & 15, 2019 (Tues., Wed. & Thurs.) | LCCMR Site Visit (NW/NE)
13 | 3 | August 20, 21 & 22, 2019 (Tues., Wed. & Thurs.) | LCCMR Site Visit (SW/SE)
14 | 2 | September 11 & 12, 2019 (Wed. & Thurs.) | LCCMR Site Visit (Metro)
15 | 2 | October 15-16 (Tues. & Wed.) | Possible Workshop
16 | 1 | November 13, 2019 (Wed.) | LCCMR Meeting: Strategic Planning
17 | 1 | December 4, 2019 (Wed.) | LCCMR Meeting: Review language for 2019 recommendations; report back on completed projects; peer review results for 2020 recommendations; discuss 2021 RFP, discuss strategic plan
18 | 1 | December 12, 2019 (Thurs.) | LCCMR Meeting: Adopt language for 2020 recommendations; adopt 2019 strategic plan; adopt 2021 RFP; adopt 2020 calendar
19 | 1 | January xx, 2020 | LCCMR Meeting: Adopt language for 2020 recommendations; adopt 2019 strategic plan; adopt 2021 RFP; adopt 2020 calendar
20 | 1 | January xx, 2020 | LCCMR Meeting: Adopt language for 2020 recommendations; adopt 2019 strategic plan; adopt 2021 RFP; adopt 2020 calendar
Issue 2021 Request for Proposal (RFP), January 2020