

**Environment and Natural Resources Trust Fund**

# M.L. 2020 Final Work Plan

## **General Information**

**ID Number:** 2020-076

**Staff Lead:** Michael Varien

**Date this document submitted to LCCMR:** August 6, 2021

**Project Title:** Lawns To Legumes Program Phase 2

**Project Budget:** $998,000

## **Project Manager Information**

**Name:** Dan Shaw

**Organization:** Board of Water and Soil Resources

**Office Telephone:** (612) 236-6291

**Email:** dan.shaw@state.mn.us

**Web Address:** https://bwsr.state.mn.us

## **Project Reporting**

**Date Work Plan Approved by LCCMR:**

**Reporting Schedule:** April 1 / October 1 of each year.

**Project Completion:** June 30, 2023

**Final Report Due Date:** August 14, 2023

## **Legal Information**

**Legal Citation:** M.L. 2021, First Special Session, Chp. 6, Art. 5, Sec. 2, Subd. 08m & 20b

**Appropriation Language:** $118,000 the second year is from the trust fund to the Board of Water and Soil Resources for demonstration projects that provide grants or payments to plant residential lawns with native vegetation and pollinator-friendly forbs and legumes to protect a diversity of pollinators. The board must establish criteria for grants or payments awarded under this section. Grants or payments awarded under this section may be made for up to 75 percent of the costs of the project, except that in areas identified by the United States Fish and Wildlife Service as areas where there is a high potential for rusty patched bumble bees to be present, grants may be awarded for up to 90 percent of the costs of the project.  
  
The following amounts, estimated to be $880,000, are transferred to the Board of Water and Soil Resources for demonstration projects that provide grants or payments to plant residential lawns with native vegetation and pollinator-friendly forbs and legumes to protect a diversity of pollinators. The board must establish criteria for grants or payments awarded under this clause. Grants or payments awarded under this clause may be made for up to 75 percent of the costs of the project, except that in areas identified by the United States Fish and Wildlife Service as areas where there is a high potential for rusty patched bumble bees to be present, grants may be awarded for up to 90 percent of the costs of the project:  
(1) the unencumbered amount, estimated to be $380,000, in Laws 2016, chapter 186, section 2, subdivision 9, paragraph (b), Minnesota Point Pine Forest Scientific and Natural Area Acquisition; and  
(2) the unencumbered amount, estimated to be $500,000, in Laws 2018, chapter 214, article 4, section 2, subdivision 6, paragraph (d), Developing RNA Interference to Control Zebra Mussels.  
  
  
(d) Transfers and Availability   
The transfers under this subdivision are effective June 30, 2021, and the transferred amounts are available until June 30, 2023.

**Appropriation End Date:** June 30, 2023

## **Narrative**

**Project Summary:** Phase Two of the Lawns to Legumes Program builds on current momentum to further engage residents across Minnesota to establish pollinator habitat and expands into community spaces.

**Describe the opportunity or problem your proposal seeks to address. Include any relevant background information.**

Minnesota’s State Bee, the Rusty patched bumble bee, as well as many other pollinators, are at risk and Minnesota residents are motivated to support these species. The Lawns to Legumes Program has received significant attention in Minnesota and nationally as an effective model for benefiting pollinators on residential landscapes and providing other environmental benefits. The first phase of the program established strong partnerships, technical resources and coaches around the state. Having this structure and public awareness in place, as well as a large number of applications submitted statewide for assistance creates a well-timed opportunity to further engage and assist Minnesota communities and residents. In Phase one, the program had funding to support only 13 of 34 Demonstration Neighborhood applications, and many additional communities have expressed interest. There is also strong interest for the Demonstration Neighborhood grant expansion into school and community park landscapes. Over 10,000 applications are expected by late fall of 2020 for the phase one Individual Support component of the program, but current program resources allow only around 1000 applicants to be funded.

**What is your proposed solution to the problem or opportunity discussed above? i.e. What are you seeking funding to do? You will be asked to expand on this in Activities and Milestones.**

Phase two of this project builds on program momentum to further engage residents statewide to establish pollinator habitat through funding opportunities and technical assistance. The program has high demand for grant assistance from both Demonstration Neighborhoods and Individual Landowner Support. Phase 2 will help meet the demand for grant assistance from communities and residents by expanding outreach to greater-Minnesota through online workshops and webinars, and expanding Demonstration Neighborhood projects to include community parks and school properties to create larger pollinator corridors and refuge areas.   
To meet its goals the program will continue to focus on the following three components:   
1) A competitive RFP for Local Partners to Build Targeted “Demonstration Neighborhoods” focused on establishing projects across neighborhoods in pollinator corridors that provide high value to the Rusty Patched Bumblebee and other at-risk pollinators. Phase two will expand to provide opportunities to fund pollinator habitat in community parks and schools landscapes.  
2) Individual Landowner Support provides a combination of cost share funding, workshops, webinars, coaching, signage, and free planting guides to residents across Minnesota.  
3) A Social Media and Education Campaign partners with conservation organizations across Minnesota to increase awareness about at-risk pollinators and the importance of creating pollinator habitat.

**What are the specific project outcomes as they relate to the public purpose of protection, conservation, preservation, and enhancement of the state’s natural resources?**

1) Increase populations of the endangered Rusty patched bumblebee and other at-risk pollinators.  
2) Develop 12-18 high profile Demonstration Neighborhood projects that restore important pollinator corridors/pathways and include a combination of residential landscapes and community spaces that build overall interest in ecological landscaping.  
4) Assist approximately 900 -1,300 landowners with funding and technical assistance while also supporting landowners who want to conduct projects on their own through technical information and guidance (involving over 10,000 landowners).  
5) Involve a wide range of conservation partners in the program as volunteer Coaches, including Master Gardeners, Master Water Steward

## **Project Location**

**What is the best scale for describing where your work will take place?** Statewide

**What is the best scale to describe the area impacted by your work?** Statewide

**When will the work impact occur?** During the Project

## **Activities and Milestones**

### **Activity 1: Competitive RFP for Local Partners to Build Targeted “Demonstration Neighborhoods”**

**Activity Budget:** $690,000

**Activity Description:**This component of the program will involve development of a competitive RFP for local partners to build targeted “Demonstration Neighborhoods” with landowners. Eligible applicants will include cities, counties, watershed districts, conservation districts, tribes and non-profit organizations. They will provide technical and financial assistance to around 330 landowners and 14 community spaces that build pollinator pathways and provide high quality habitat for at-risk pollinators.   
  
A technical advisory team hosted by BWSR will rank proposals based on:   
A) Location within rusty-patched bumble bee priority areas and the range of other at-risk pollinators  
B) Location within or connecting to other key habitat corridors and/or public investments in habitat   
C) Technical Expertise involved in projects  
D) Likely longevity of projects  
E) Strength of partnerships and match  
F) Demographic, social equity, geographic distribution  
G) Potential to build community interest/momentum  
  
After grants are awarded the recipients will coordinate with landowners to plan, install and provide reimbursements for the pollinator-friendly plantings. Landowners will have access to technical resources developed through Activity #3 of this workplan, including the program guide, and planting templates, as well as signage (part of activity #2) to increase their engagement and knowledge about pollinator conservation.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Development of grant criteria and request for proposal | November 30, 2021 |
| Award twelve to eighteen projects ($20,000 - $40,000 each) for plantings in corridors | March 31, 2022 |
| Distribute Lawns to Legumes pollinator planting signage to Demonstration Neighborhood grantees | December 31, 2022 |
| Approximately 13-16 Demonstration Neighborhoods established with new plantings within high priority pollinator corridors | June 30, 2023 |
| Collect all required final reporting documentation | June 30, 2023 |

### **Activity 2: Individual Landowner Support**

**Activity Budget:** $301,000

**Activity Description:**This component of the program is focused on providing a combination of cost share funding, coaching, signage and free planting guides to residents across Minnesota. This component will be coordinated though the Blue Thumb Partnership that has run the Individual Support component of Phase one of Lawns to Legumes. Support will be provided to 600-900 landowners as well as project recognition through signage to all participants. Residents can apply for up to $300 of cost-share funding and are expected to provide at least 25% cash or in kind match.   
80-100 coaches will be involved in assisting 450-500 residents.  
Residential is defined as land or parcels associated with residential occupancy including single family homes, apartments and similar types of multifamily dwellings, as well as community spaces that are apart of or adjacent to these residences. This includes rural residences. Excluded from this definition are agricultural, commercial, industrial or natural lands not associated with a residence.  
  
Demonstration Neighborhoods will use $50K and Individual Support will use $30K from reimbursement requests toward: (M.L. 2021, First Special Session, Chp. 06, Art. 05, Sec. 02, Subd. 08m funds available until June 30, 2024). We will spend down the Subd. 20b line items first.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Targeted distribution of Individual Support grants to 220-300 residents | March 31, 2022 |
| Targeted distribution of Individual Support grants to 220-300 residents | June 30, 2022 |
| Lawns to Legumes pollinator planting signs distributed to Individual grantees after reimbursement request submitted. | December 31, 2022 |
| Targeted distribution of Individual Support grants to 220 - 300 residents | December 31, 2022 |
| Final collection of Individual Support program reimbursement request items and summary of program report. | June 30, 2023 |

### **Activity 3: Social Media Outreach and Education Campaign**

**Activity Budget:** $7,000

**Activity Description:**The Social Media Outreach and Education Campaign involves a partnership with conservation organizations across Minnesota to increase awareness about at-risk pollinators and the importance of creating pollinator habitat. This component will encourage and assist landowners who want to conduct habitat projects on their own through outreach, technical information and guidance (involving over 10,000 landowners). Key aspects of this component will include implementation of the program’s communications and marketing plan, social media, articles, displays and other communication with residents, as well as promotion of the program habitat guide and collaboration with the Minneapolis College of Art and Design students on outreach and graphic communication. The program outreach resources will also support activity 1 and 2 of this program.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Collaboration with Minneapolis College of Art and Design students on outreach and graphics | June 30, 2022 |
| Conduct partner coordinated outreach to the public at least six times a year | June 30, 2023 |
| Implementation of the program’s communications plan to guide the social media campaign and collaboration between Partners | June 30, 2023 |

## **Project Partners and Collaborators**

|  |  |  |  |
| --- | --- | --- | --- |
| **Name** | **Organization** | **Role** | **Receiving Funds** |
| Becky Rice | Metro Blooms/Blue Thumb Partnership | The Blue Thumb Partnership consists of 50+ conservation members that have been conducting landowner workshops since 2007 and coordinated the Individual Support component of phase 1. They will continue with the same role in phase 2 | Yes |

## **Dissemination**

**Describe your plans for dissemination, presentation, documentation, or sharing of data, results, samples, physical collections, and other products and how they will follow ENRTF Acknowledgement Requirements and Guidelines.**The program will acknowledge the Environment and Natural Resources Trust Fund through use of the trust fund logo or attribution language on project print and electronic media, publications, signage, and other communications per the ENTRF Acknowledgment Guidelines.

## **Long-Term Implementation and Funding**

**Describe how the results will be implemented and how any ongoing effort will be funded. If not already addressed as part of the project, how will findings, results, and products developed be implemented after project completion? If additional work is needed, how will this be funded?**This project builds upon ongoing work of Lawns to Legumes Phase 1 that includes Demonstration Neighborhoods, Individual Support, and Outreach components. Both Phases of funding will focus on these three components and will overlap efforts in 2021, 2022 and 2023. Phase 2 will fund additional Demonstration Neighborhoods (including expansion into school and park landscapes) and individual residents through the Individual Support Component of the program. Additional funding sources are being pursued to continue Lawns to Legumes as a key BWSR program into the future, as it has a strong structure with its partnerships, technical resources and trained coaches.

## **Other ENRTF Appropriations Awarded in the Last Six Years**

|  |  |  |
| --- | --- | --- |
| **Name** | **Appropriation** | **Amount Awarded** |
| Northeast Minnesota White Cedar Restoration - Phase 2 | M.L. 2014, Chp. 226, Sec. 2, Subd. 06d | $335,000 |
| Minnesota Conservation Apprenticeship Academy | M.L. 2014, Chp. 226, Sec. 2, Subd. 09a | $392,000 |
| Acceleration of Minnesota Conservation Assistance - Final Phase | M.L. 2015, Chp. 76, Sec. 2, Subd. 08d | $1,000,000 |
| Conservation Reserve Enhancement Program (CREP) Outreach and Implementation | M.L. 2017, Chp. 96, Sec. 2, Subd. 08k | $6,000,000 |
| Lawns to Legumes | M.L. 2019, First Special Session, Chp. 4, Art. 2, Sec. 2, Subd. 08f | $900,000 |

## **Budget Summary**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Category / Name** | **Subcategory or Type** | **Description** | **Purpose** | **Gen. Ineli gible** | **% Bene fits** | **# FTE** | **Class ified Staff?** | **$ Amount** |
| **Personnel** |  |  |  |  |  |  |  |  |
| Program Staff |  | Program Implementation, Grant oversight, approval of activities and approval of payments (M.L. 2021, First Special Session, Chp. 06, Art. 05, Sec. 02, Subd. 08m funds available until June 30, 2024) |  |  | 22% | 1.02 | X | $19,000 |
| Program Coordinator |  | Coordination of the Grant Program (M.L. 2021, First Special Session, Chp. 06, Art. 05, Sec. 02, Subd. 08m funds available until June 30, 2024) |  |  | 22% | 0.81 |  | $19,000 |
| Grant Coordinator |  | Processing and distribution of funding |  |  | 22% | 0.12 | X | $3,000 |
| Program Coordinator |  | Coordination of the Grant Program |  |  | 22% | 0.84 |  | $40,000 |
| Program Stafff |  | Program Implementation, Grant oversight, approval of payments |  |  | 22% | 1.02 | X | $53,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$134,000** |
| **Contracts and Services** |  |  |  |  |  |  |  |  |
| Blue Thumb/Metro Blooms Partnership | Sub award | Metro Blooms coordinates the Individual Support component of the program including awarding $200,000 of individual support funding ($30,000), coordinating with MCAD, coordinating coaching of individual support recipients ($25,000), and printing signs ($18,500) and shipping ($1,500) of 1500 signs, and MCAD outreach collaboration ($6,000) |  |  |  | 0.57 |  | $251,000 |
| Grant Funding for Demonstration Neighborhoods Component of Program | Sub award | Demonstration Neighborhood grant recipients (12-18 recipients) are responsible for working with individual residents and community park staff that are part of demonstration neighborhood projects to guide their project planning, installation and management. |  |  |  | 1.17 |  | $526,000 |
| Individual Support Component | Sub award | Metro Blooms coordinates the Individual Support component of the program including awarding $200,000 of individual support funding.(M.L. 2021, First Special Session, Chp. 06, Art. 05, Sec. 02, Subd. 08m funds available until June 30, 2024). We will spend down the Subd. 20b line items first. |  |  |  | 0.3 |  | $30,000 |
| Demonstration Neighborhood Component | Sub award | Demonstration Neighborhood grant recipients (12-18 recipients) are responsible for working with individual residents and community park staff (M.L. 2021, First Special Session, Chp. 06, Art. 05, Sec. 02, Subd. 08m funds available until June 30, 2024). We will spend down the Subd. 20b line items first. |  |  |  | 0.3 |  | $50,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$857,000** |
| **Equipment, Tools, and Supplies** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Capital Expenditures** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Acquisitions and Stewardship** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Travel In Minnesota** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Travel Outside Minnesota** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Printing and Publication** |  |  |  |  |  |  |  |  |
|  | Printing | Printing of approximately 400 habitat guides | Outreach to be used at tabling events for the program |  |  |  |  | $2,000 |
|  | Printing | Lawns to Legumes Stickers (1000) | Outreach at events |  |  |  |  | $500 |
|  | Printing | 2000 brochures | Outeach at events |  |  |  |  | $500 |
|  | Printing | Lawns to Legumes Gardening Gloves | Outreach at events |  |  |  |  | $2,000 |
|  | Printing | Flyers | Outreach at events |  |  |  |  | $2,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$7,000** |
| **Other Expenses** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
|  |  |  |  |  |  |  | **Grand Total** | **$998,000** |

### **Classified Staff or Generally Ineligible Expenses**

|  |  |  |  |
| --- | --- | --- | --- |
| **Category/Name** | **Subcategory or Type** | **Description** | **Justification Ineligible Expense or Classified Staff Request** |
| **Personnel** - Program Staff |  | Program Implementation, Grant oversight, approval of activities and approval of payments (M.L. 2021, First Special Session, Chp. 06, Art. 05, Sec. 02, Subd. 08m funds available until June 30, 2024) | **Classified :** This position is essential to the program to conduct program implementation, and grant oversight for Demonstration Neighborhood recipients. ENRTF funds are not being used to supplant other sources of funds traditionally used to pay for that classified staff salary. |
| **Personnel** - Grant Coordinator |  | Processing and distribution of funding | **Classified :** This position is necessary for the project to develop grant agreements and oversee the distribution of grants for Demonstration Neighborhoods. ENRTF funds are not being used to supplant other sources of funds traditionally used to pay for that classified staff salary. |
| **Personnel** - Program Stafff |  | Program Implementation, Grant oversight, approval of payments | **Classified :** This position is essential to the program to conduct program implementation, and grant oversight for Demonstration Neighborhood recipients. ENRTF funds are not being used to supplant other sources of funds traditionally used to pay for that classified staff salary. |

### **Non ENRTF Funds**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Category** | **Specific Source** | **Use** | **Status** | **Amount** |
| **State** |  |  |  |  |
|  |  |  | **State Sub Total** | **-** |
| **Non-State** |  |  |  |  |
| In-Kind | 25% Match from residents for pollinator plantings as part of Individual Support and Demonstration Neighborhood components of the Program | Funding will be used as part of the installation and management of the pollinator plantings. | Pending | $150,000 |
|  |  |  | **Non State Sub Total** | **$150,000** |
|  |  |  | **Funds Total** | **$150,000** |

## **Acquisition and Restoration**

### **Parcel List**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Name** | **County** | **Site Significance** | **Activity** | **Acres** | **Miles** | **Estimated Cost** | **Type of Landowner** | **Easement or Title Holder** | **Status of Work** |
| TBD |  |  |  | - | - | - |  |  |  |
| **Totals** |  |  |  | **0** | **0** | **-** |  |  |  |

### **Restoration**

**1. Provide a statement confirming that all restoration activities completed with these funds will occur on land permanently protected by a conservation easement or public ownership.**Community spaces that are funded through this program will be the areas where ecological restoration activities will be conducted and protected by public ownership. The smaller residential plantings will occur on private property as was conducted as part of phase one of Lawns to Legumes.

**2. Summarize the components and expected outcomes of restoration and management plans for the parcels to be restored by your organization, how these plans are kept on file by your organization, and overall strategies for long-term plan implementation.**A restoration plan template that includes site preparation, installation and management guidance will be developed to be adapted for individual projects will be used for community spaces that will be restored through the program. These plans will be required to be uploaded to BWSR's eLINK reporting system. The plan templates will also act as long-term stewardship plans to provide guidance to landowners for long-term management of the restoration.

**3. Describe how restoration efforts will utilize and follow the Board of Soil and Water Resources “Native Vegetation Establishment and Enhancement Guidelines” in order to ensure ecological integrity and pollinator enhancement.**Projects will require that high quality native seed and appropriate species are selected for the project and that the seed source sequence, diversity recommendations, seed specifications and climate considerations in the Native Vegetation Establishment and Enhancement Guidelines be followed for projects. Seed tags must also be retained for documentation of what seed was installed.

**4. Describe how the long-term maintenance and management needs of the parcel being restored with these funds will be met and financed into the future.**The restoration plan developed for projects will include long-term management guidance. Any projects being restored through the program will be required to sign a stewardship agreement stating that long-term management will be conducted and how the work will be funded in the future.

**5. Describe how consideration will be given to contracting with Conservation Corps of Minnesota for any restoration activities.**Conservation Corps of Minnesota's website link will be added to BWSR's Lawns to Legumes website so that program participants can contact them as a resource.

**6. Provide a statement indicating that evaluations will be completed on parcels where activities were implemented both 1) initially after activity completion and 2) three years later as a follow-up. Evaluations should analyze improvements to the parcel and whether goals have been met, identify any problems with the implementation, and identify any findings that can be used to improve implementation of future restoration efforts at the site or elsewhere.**Evaluations of projects will be completed initially after activity completion and three years later to assess goals, identify problems and gather information about successful strategies that can be included in BWSR's What's Working webpage. This evaluation is consistent with site assessments conducted for BWSR funded projects.

## **Attachments**

### **Required Attachments**

#### ***Map***

File: [b8303e8c-719.pdf](https://lccmrprojectmgmt.leg.mn/media/map/b8303e8c-719.pdf)

#### ***Alternate Text for Map***

This graphic shows current phase one accomplishments for the Lawns to Legumes program including 7500 resident applications for funding support, launch of the program at the state fair, Oprah Magazine feature with a circulation of 2.4 million, pollinator planting DIY tools accessed 33,351 times, and 14 resident workshops with 815 residents trained. The back side of the graphic includes the lawn sign for the program....

### **Optional Attachments**

#### ***Support Letter or Other***

|  |  |
| --- | --- |
| **Title** | **File** |
| Background Check | [7d45b218-915.pdf](https://lccmrprojectmgmt.leg.mn/media/attachments/7d45b218-915.pdf) |

## **Difference between Proposal and Work Plan**

#### ***Describe changes from Proposal to Work Plan Stage***

This workplan is very similar to BWSR's workplan for Phase 2 of Lawns to Legumes (993,000 appropriation) but reflects an updated budget for the transferred $998,000. A higher percentage of funding is being directed to the demonstration neighborhoods compared to individual support projects as compared to the workplan for the $993,000. This workplan also removed direct reference to "school landscapes" as part of the demonstration neighborhood projects to use the more generalized terminology of "community spaces". Duplication of match sources was removed from this workplan that overlapped with the workplan for Lawns to Legumes Phase 2 ($993,000 appropriation) to avoid counting the match twice.

## **Additional Acknowledgements and Conditions:**

The following are acknowledgements and conditions beyond those already included in the above workplan:

**Do you understand and acknowledge the ENRTF repayment requirements if the use of capital equipment changes?**   
 N/A

**Do you agree travel expenses must follow the "Commissioner's Plan" promulgated by the Commissioner of Management of Budget or, for University of Minnesota projects, the University of Minnesota plan?**   
 N/A

**Does your project have potential for royalties, copyrights, patents, or sale of products and assets?**   
 No

**Do you understand and acknowledge IP and revenue-return and sharing requirements in 116P.10?**   
 N/A

**Do you wish to request reinvestment of any revenues into your project instead of returning revenue to the ENRTF?**   
 N/A

**Does your project include original, hypothesis-driven research?**   
 No

**Does the organization have a fiscal agent for this project?**   
 No