

**Environment and Natural Resources Trust Fund**

# M.L. 2025 Final Work Plan

## **General Information**

**ID Number:** 2025-084

**Staff Lead:** Lisa Bigaouette

**Date this document submitted to LCCMR:** June 5, 2025

**Project Title:** Cyanotoxins in Minnesota Lakes: The Role of Sunlight

**Project Budget:** $220,000

## **Project Manager Information**

**Name:** William Arnold

**Organization:** U of MN - College of Science and Engineering

**Office Telephone:** (612) 625-8582

**Email:** arnol032@umn.edu

**Web Address:** https://cse.umn.edu/

## **Project Reporting**

**Reporting Schedule:** March 1 / September 1 of each year.

**Project Completion:** June 30, 2028

**Final Report Due Date:** August 14, 2028

## **Legal Information**

**Legal Citation:** M.L. 2025, First Special Session, Chp. 1, Art. 2, Sec. 2, Subd. 04f

**Appropriation Language:** $220,000 the first year is from the trust fund to the Board of Regents of the University of Minnesota to quantify degradation of cyanobacterial toxins by sunlight to understand how increasing frequency of harmful algal blooms and changing environmental conditions influence toxin persistence in natural waters.

**Appropriation End Date:** June 30, 2028

## **Narrative**

**Project Summary:** The degradation of cyanobacterial toxins by sunlight will be quantified to understand how increasing frequency of cyanobacterial (harmful algal) blooms and changing environmental conditions influence toxin persistence in natural waters.

**Describe the opportunity or problem your proposal seeks to address. Include any relevant background information.**

The combination of increased temperatures and nutrient loads to Minnesota’s lakes and rivers are increasing the duration and frequency of blooms of harmful cyanobacteria (also known as harmful algal blooms). These blooms produce cyanotoxins that are a threat to humans who drink or recreate in Minnesota’s waters as well as wildlife. Additionally, these blooms will affect the composition of dissolved organic matter (DOM), the material that gives water its brown color in lakes and rivers. When the DOM absorbs sunlight, it creates reactive species that are critical to the degradation of a cyanotoxins. Yet the presence of cyanobacteria and cyanobacterial organic matter will influence the production and quenching of these same reactive intermediates in natural waters. Additionally, we do not fully understand how different wavelengths of light influence this process. Due to stratospheric ozone recovery and the emission of more greenhouse gases and other particles into the atmosphere, many bodies of water will experience a future shift in the intensity and spectrum of sunlight they receive. We do not know how this combination of conditions will affect the longevity of cyanotoxins in Minnesota’s waters.

**What is your proposed solution to the problem or opportunity discussed above? Introduce us to the work you are seeking funding to do. You will be asked to expand on this proposed solution in Activities & Milestones.**

This proposal seeks to address how the cascading effects of temperature, nutrients, organic matter composition and changes in sunlight will affect the persistence of cyanotoxins in Minnesota waters, so we can develop better warnings about water use and recommendations for additional treatment of drinking water. Using a combination of laboratory grown cyanobacteria and waters collected from lakes before, during, and after cyanobacteria blooms, the production of reactive intermediates by cyanobacterial organic matter will be measured and compared to materials present in unimpacted waters. The effect of different wavelengths of light will be tested. From this information, the production rate of reactive intermediates will be calculated and used to predict how the concentrations of cyanotoxins in Minnesota lakes will change under different scenarios. The levels of cyanotoxins in the lakes and the rate at which these toxins degrade in the presence of different organic matter will then be measured directly. Finally, the specific reactive species responsible for the degradation of the cyanotoxins will be identified, and this data will provide the information needed to assess how different environmental conditions affect the persistence of cyanotoxins in Minnesota lakes.

**What are the specific project outcomes as they relate to the public purpose of protection, conservation, preservation, and enhancement of the state’s natural resources?**

Understanding cyanotoxin persistence in our water is important for the protection of all water users. Furthermore, the presence of cyanotoxins poses a threat to the fish and other aquatic life that live in these waters. Understanding how the cascading effects of temperature, light, and water quality will affect the surface-water photochemistry and longevity of cyanotoxins in Minnesota’s waters will be critically important for management decisions, public notification of potential dangers, and adaptive drinking water treatment.

## **Project Location**

**What is the best scale for describing where your work will take place?** Statewide

**What is the best scale to describe the area impacted by your work?** Statewide

**When will the work impact occur?** During the Project and In the Future

## **Activities and Milestones**

### **Activity 1: Quantify the ability of cyanobacterial organic matter to produce reactive intermidiates that can degrade cyanobacterial toxins**

**Activity Budget:** $130,000

**Activity Description:**A cyanobacterial strain (M. aeruginosa strain UTEX B 2662) known to produce cyanotoxins will be grown in the laboratory. Once the culture is established, the water will be filtered/extracted to collect the organic matter. Water samples from lakes, including sentinel lakes monitored by the Minnesota Pollution Control Agency, will be collected before, during, and after cyanobacterial blooms. These waters and the material collected from the lab grown strain will be used in photochemistry experiments. The spectral and chemical properties of the organic matter will be characterized. A series of chemical probes will be used to quantify hydroxyl radicals, carbonate radials, singlet oxygen, and reactive triplet species from the organic matter. These are the reactive intermediates likely to degrade cyanotoxins. Comparisons will be made to the production of the reactive intermediates from reference organic material, collected from lakes without cyanobacterial blooms. The light wavelength dependence of these reactions will be explored by comparing the reactive intermediate production at a range of wavelengths using a solar simulator and narrow bandwidth light emitting diodes (LEDs).

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Approximate Completion Date** |
| Grow cyanobacterial cultures and harvest organic matter | December 31, 2025 |
| Collect cyanobacterial bloom impacted waters | October 31, 2026 |
| Experiments to quantify reactive intermediates - solar light | October 31, 2026 |
| Manuscript publication | December 31, 2026 |
| Experiments to quantify reactive intermediates - light emitting diodes | March 31, 2027 |

### **Activity 2: Establish the rate and pathway of cyanobacterial toxin degradation under different light and solution conditions**

**Activity Budget:** $90,000

**Activity Description:**The degradation of cyanotoxins when exposed to light in the presence of organic matter will be explored. Probe and quencher experiments will be used to isolate the specific reactive species responsible for the degradation. Known reactive intermediate sensitizers will be used to verify the reactivity and determine the second order rate constants. The effect of light wavelength will again be explored by comparing cyanotoxin degradation at a range of wavelengths using a solar simulator and narrow bandwidth light emitting diodes. The information about reactive intermediate production from Activity 1 and the degradation rate constants in Activity 2 will be combined into a model that will be able to predict cyanotoxin persistence for various organic matter compositions and light intensities/spectra.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Approximate Completion Date** |
| Confirm cyanobacterial toxin analytical method | October 31, 2025 |
| Measurement of cyanobacterial compound degradation - solar light and light emitting diodes | January 31, 2027 |
| Measure rates of cyanobacterial compound degradation - solution conditions | March 31, 2027 |
| Model development | June 30, 2027 |
| Manuscript publication | June 30, 2027 |

## **Dissemination**

**Describe your plans for dissemination, presentation, documentation, or sharing of data, results, samples, physical collections, and other products and how they will follow ENRTF Acknowledgement Requirements and Guidelines.**Dissemination efforts will include peer-review publications and presentations at local/regional conference (e.g., the annual Minnesota Water Conference). We will also set up meetings or seminars with agencies (e.g., the Minnesota Pollution Control Agency, Minnesota Department of Health), drinking water utilities (St. Paul Regional Water Services), and other researchers (St Croix Watershed Research Station) to facilitate information exchange and sharing our findings. These interactions will foster information transmittal to stakeholders and the public. Relevant field data will be archived in the data repository for the University of Minnesota, which is open access. The Environment and Natural Resources Trust Fund will be acknowledged through use of the trust fund logo or attribution language on project print and electronic media, publications, signage, and other communications per the ENTRF Acknowledgment Guidelines.

## **Long-Term Implementation and Funding**

**Describe how the results will be implemented and how any ongoing effort will be funded. If not already addressed as part of the project, how will findings, results, and products developed be implemented after project completion? If additional work is needed, how will this work be funded?**The results will be communicated to stakeholders, including state agencies, watershed districts, and science/engineering consulting firms, through direct communication, presentation and local/regional conferences, and peer-reviewed publications.

## **Other ENRTF Appropriations Awarded in the Last Six Years**

|  |  |  |
| --- | --- | --- |
| **Name** | **Appropriation** | **Amount Awarded** |
| Determining Influence of Insecticides on Algal Blooms | M.L. 2019, First Special Session, Chp. 4, Art. 2, Sec. 2, Subd. 04a | $350,000 |
| Benign Design: Environmental Studies Leading to Sustainable Pharmaceuticals | M.L. 2019, First Special Session, Chp. 4, Art. 2, Sec. 2, Subd. 04b | $415,000 |
| Improving Drinking Water for Minnesotans through Pollution Prevention | M.L. 2019, First Special Session, Chp. 4, Art. 2, Sec. 2, Subd. 04f | $345,000 |
| Technology For Energy-Generating Onsite Industrial Wastewater Treatment | M.L. 2021, First Special Session, Chp. 6, Art. 5, Sec. 2, Subd. 04b | $450,000 |
| Microgeographic Impact of Antibiotics Released from Identified Hotspots | M.L. 2021, First Special Session, Chp. 6, Art. 6, Sec. 2, Subd. 04d | $508,000 |
| Finding, Capturing, and Destroying PFAS in Minnesota Waters | M.L. 2023, , Chp. 60, Art. 2, Sec. 2, Subd. 04d | $478,000 |
| Removing CECs from Stormwater with Biofiltration | M.L. 2023, , Chp. 60, Art. 2, Sec. 2, Subd. 04j | $641,000 |

## **Budget Summary**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Category / Name** | **Subcategory or Type** | **Description** | **Purpose** | **Gen. Ineli gible** | **% Bene fits** | **# FTE** | **Class ified Staff?** | **$ Amount** |
| **Personnel** |  |  |  |  |  |  |  |  |
| William Arnold |  | Project Manager |  |  | 27% | 0.16 |  | $57,800 |
| Graduate Student Research Assistant |  | Laboratory work |  |  | 44% | 0.94 |  | $106,785 |
|  |  |  |  |  |  |  | **Sub Total** | **$164,585** |
| **Contracts and Services** |  |  |  |  |  |  |  |  |
| TBD | Internal services or fees (uncommon) | analytical fees in UMN central laboratory facilities |  |  |  | - |  | $8,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$8,000** |
| **Equipment, Tools, and Supplies** |  |  |  |  |  |  |  |  |
|  | Tools and Supplies | Laboratory supplies | Chemicals, solvents, and material to conduct the work |  |  |  |  | $23,415 |
|  | Tools and Supplies | Instrument maintenance | Support for upkeep of mass spectrometry system |  |  |  |  | $12,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$35,415** |
| **Capital Expenditures** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Acquisitions and Stewardship** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Travel In Minnesota** |  |  |  |  |  |  |  |  |
|  | Miles/ Meals/ Lodging | Anticipate up to 6 trips per year, up to 200 miles, 2 people per trip. | Travel to lakes to collect samples before, during, and after blooms. |  |  |  |  | $2,500 |
|  | Conference Registration Miles/ Meals/ Lodging | Two conference events in Minnesota (e.g., MN AWWA, MN Water Conference) | Present results to community/stakeholders |  |  |  |  | $1,500 |
|  |  |  |  |  |  |  | **Sub Total** | **$4,000** |
| **Travel Outside Minnesota** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Printing and Publication** |  |  |  |  |  |  |  |  |
|  | Publication | Open access fees | Provide maximum exposure for publications |  |  |  |  | $8,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$8,000** |
| **Other Expenses** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
|  |  |  |  |  |  |  | **Grand Total** | **$220,000** |

### **Classified Staff or Generally Ineligible Expenses**

|  |  |  |  |
| --- | --- | --- | --- |
| **Category/Name** | **Subcategory or Type** | **Description** | **Justification Ineligible Expense or Classified Staff Request** |

### **Non ENRTF Funds**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Category** | **Specific Source** | **Use** | **Status** | **$ Amount** |
| **State** |  |  |  |  |
|  |  |  | **State Sub Total** | **-** |
| **Non-State** |  |  |  |  |
| In-Kind | U of MN Indirect Costs | UMN facilities and administration | Secured | $101,000 |
|  |  |  | **Non State Sub Total** | **$101,000** |
|  |  |  | **Funds Total** | **$101,000** |

**Total Project Cost: $321,000**

**This amount accurately reflects total project cost?**  
 Yes

## **Attachments**

### **Required Attachments**

#### ***Visual Component***

File: [bc67b027-5da.pdf](https://lccmrprojectmgmt.leg.mn/media/map/bc67b027-5da.pdf)

#### ***Alternate Text for Visual Component***

A picture of a sunlit lake with green growth (cyanobacteria) due to the presence of nutrients, light, and heat. The cyanobacteria generate toxins, and these are degraded by reactive species generated by sunlight. Understanding the details of this cycle is key to protecting humans and wildlife from these toxins....

### **Supplemental Attachments**

#### ***Capital Project Questionnaire, Budget Supplements, Support Letter, Photos, Media, Other***

|  |  |
| --- | --- |
| **Title** | **File** |
| Approval to Submit - UMN | [c4fdf656-49a.pdf](https://lccmrprojectmgmt.leg.mn/media/attachments/c4fdf656-49a.pdf) |
| 2025-084 Research Addendum revised\_final | [91d6d537-5a5.docx](https://lccmrprojectmgmt.leg.mn/media/attachments/91d6d537-5a5.docx) |

## **Difference between Proposal and Work Plan**

#### ***Describe changes from Proposal to Work Plan Stage***

Per comments, none needed.

## **Additional Acknowledgements and Conditions:**

The following are acknowledgements and conditions beyond those already included in the above workplan:

**Do you understand and acknowledge the ENRTF repayment requirements if the use of capital equipment changes?**   
 N/A

**Do you understand that travel expenses are only approved if they follow the "Commissioner's Plan" promulgated by the Commissioner of Management of Budget or, for University of Minnesota projects, the University of Minnesota plan?**  
 Yes, I understand the UMN Policy on travel applies.

**Does your project have potential for royalties, copyrights, patents, sale of products and assets, or revenue generation?**   
 No

**Do you understand and acknowledge IP and revenue-return and sharing requirements in 116P.10?**   
 N/A

**Do you wish to request reinvestment of any revenues into your project instead of returning revenue to the ENRTF?**   
 N/A

**Does your project include original, hypothesis-driven research?**   
 Yes

**Does the organization have a fiscal agent for this project?**   
 No

**Does your project include the pre-design, design, construction, or renovation of a building, trail, campground, or other fixed capital asset costing $10,000 or more or large-scale stream or wetland restoration?**  
 No

**Do you propose using an appropriation from the Environment and Natural Resources Trust Fund to conduct a project that provides children's services (as defined in Minnesota Statutes section 299C.61 Subd.7 as "the provision of care, treatment, education, training, instruction, or recreation to children")?**  
 No

**Provide the name(s) and organization(s) of additional individuals assisting in the completion of this project:**

Katie Sauer (budget)

**Do you understand that a named service contract does not constitute a funder-designated subrecipient or approval of a sole-source contract? In other words, a service contract entity is only approved if it has been selected according to the contracting rules identified in state law and policy for organizations that receive ENRTF funds through direct appropriations, or in the DNR’s reimbursement manual for non-state organizations. These rules may include competitive bidding and prevailing wage requirements**  
 N/A