PROJECT TITLE: Real-time monitoring of statewide pollen in Minnesota

I. PROJECT STATEMENT

This project aims to develop a low-cost and compact module that can transform a smartphone into a sensor for real-time monitoring of pollen conditions in Minnesota. The module includes a miniature phone attachment that allows in situ recording images of pollen in the air, based on digital inline holography (DIH), and a user-friendly and self-guided mobile app, which uses machine-learning based algorithm to identify and quantify different types of allergenic pollens, automatically.

Pollen is one of the main triggers of allergies which affects more than 50 million Americans each year. Studies have shown that as many as 2/3 of people who have asthma, also suffer from allergies. In Minnesota, asthma affects one in 16 children (6.4%) and one in 13 adults (7.4%). The pollen season in Minnesota typically starts in early April and ends when a hard frost occurs in the fall, which could also be lengthened by climate change (e.g. ragweed pollen season is now 18 to 21 days longer than in the mid-1990s). As winters are warming, some non-native, allergenic plants might also expand their range into Minnesota. Therefore, it becomes increasingly important to monitor statewide pollen levels as part of the daily air quality control. The pollen data could allow allergy and asthma patients to better manage their allergies by taking medication and minimize exposure to allergenic pollen through the year, such as avoiding locations where pollen is likely to be high.

Currently, websites or smartphone applications (apps) provide a forecast of the pollen count (low, medium or high) from models, based upon historical and climatological data. The National Allergy Bureau is the most trusted resource for accurate pollen counts collected at over 70 stations nationwide with the Clinical Research Institute, Inc. (CRI) being the only site in Minnesota. Despite its accuracy, the process is labor-intense. It requires collecting samples at a specific location for a 24-hour period, then manually counting the grains of each pollen type by a certified counter, under a microscope. These data overall are not sufficient to accurately forecast the types of prevalent pollen, their concentration levels, or their change over time at a given location.

With the phone attachment and app developed in this project, pollen counts will be collected in an extended geographic scale of Minnesota and be monitored in real time, by engaging citizen scientists. A spatial database of pollen levels can be created from the shared pollen counts and locations from smartphone users. Long-term tracking of individual pollen types will also be generated. This database will be made public via an interactive web interface to citizens, government agencies, health professionals and researchers.

II. PROJECT ACTIVITIES AND OUTCOMES

Activity 1: Perform lab measurements of common pollen in Minnesota using DIH

Description: This activity will involve the development of basic methodology for how to image and categorize different types of pollen grains using DIH, which has been broadly used for 3D imaging and live tracking particles yet thoroughly tested in analyzing pollen. The activity will take place at PI Hong’s lab using the existing DIH setup, which consists of a laser source and a digital camera. This setup captures distinct marks made by the pollen grains floating in the air within the laser beam path on the camera sensor, called holograms (example shown in Figure 1). The holograms are then processed using a computer program developed in Hong's lab to reconstruct the in-focused images of individual pollen grains and their 3D spatial distribution in the air column, and successively derive the size and morphology of each grain. A machine-learning algorithm will be implemented to automatically categorize different types of pollen and measure the pollen counts.

ENRTF BUDGET: $99,239

| Outcome | Completion Date |
| --- | --- |
| 1. Perform 3D imaging and analysis of pollen grains using DIH | June 2021 |
| 2. Derive general relationship between pollen holograms and physical parameters | June 2021 |
| 3. Develop a machine-learning algorithm to automatically categorize and count pollen | June 2021 |

Activity 2: Develop the phone attachment and a mobile app

Description: This activity will involve the development of a hardware attachment to the smartphone, which will consist of a low power laser as the illumination light source and a miniature lens piece attached to phone camera that converts it into a digital microscope (Figure 1). A mobile app will be developed which incorporates the hologram analysis codes and machine-learning algorithms developed in Activity 1. We will select three sites around the Twin-Cities area to collect field data through the year. The results will be compared to the pollen counts from the CRI and forecasts from websites for cross-validation on a daily basis. The hardware design and app will be optimized according to the outcomes of field tests to be compatible with the smartphone computing power, while maintaining accuracy and speed.

ENRTF BUDGET: $110,201

| Outcome | Completion Date |
| --- | --- |
| 1. Develop a phone attachment and mobile app for pollen monitoring | March 2022 |
| 2. Identify locations of test sites and collect field data | January 2022 |
| 3. Analyze field data and improve hardware and app design according to the outcomes | December 2022 |

Activity 3: Engage citizen-scientists and build a spatial database for long-term pollen monitoring

Description: We will use the finalized hardware design in Activity 2 to assemble 20 mobile phone attachments to distribute to volunteers from 10 sites statewide within the 4G network coverage area (tentative sites shown in Figure 2). A remote server will be set up at St. Anthony Falls laboratory (SAFL) to continuously receive and store the pollen data and locations from each mobile phone. A user-friendly website will be created and managed by SAFL, where a spatial map of pollen counts of each monitored type will be reported daily and open to the public. The long-term spatial database will be accessible through a web server hosted by one virtual machine through the Office of Information Technology (OIT) at the University of Minnesota and be open to the public.

ENRTF BUDGET: $109,693

| Outcome | Completion Date |
| --- | --- |
| 1. Engage citizen-scientists by distributing phone attachments and mobile app | February 2023 |
| 2. Create a spatial map of pollen counts daily and build the long-term spatial database | June 2023 |
| 3. Finish a website to report pollen counts and to provide open access to the database | June 2023 |

III. LONG-TERM IMPLEMENTATION AND FUNDING:

The long-term implementation of the developed technology from this proposal will be conducted through close collaboration with Minnesota Department of Health, Department of Natural Resources and Minnesota Pollution Control Agency to better meet their missions. We will construct an official website hosted in collaboration with state agencies to post daily pollen report which could provide a guideline for allergy and asthma patients to take proactive approaches to better manage their symptoms. Results from this research will also be disseminated in peer-reviewed journals, presented at conferences, and shared with local media outlets. The openly accessible long-term spatial database could be used by any researcher in relevant fields, for instance, to build better models for predicting onset and duration of allergenic pollen season, or to investigate the effect of climate change on pollen allergies and local forestry. The tools developed in this research, including the phone attachment and mobile app, could be leveraged in educational efforts, including the SAFL outreach program towards middle school students.

Built upon this project, we will apply funding opportunities from the Environmental Protection Agency or the National Institute of Allergy and Infectious Diseases to expand pollen monitoring nationwide and to extend the functionality of the mobile app by monitoring other air particles for indoor and outdoor air quality control.

V. SEE ADDITIONAL PROPOSAL COMPONENTS:

Proposal Budget Spreadsheet, Visual Component, Project Manager Qualifications and Organization Description