## Summary (hidden)
Project: | LCCMR_Sara Heger et al |  |  | start | end
Budget by: M. Hernick |  |  | Project dates | 2020-07-01 | 2022-06-30
Date: | 2019-03-05
Project: | Reducing Chloride in Minnesota’s Water from Water Softening
[7 empty] | Salary & Fringe | Contracts | Equip. & supplies | Capital | Travel | Total
Activity 1: Test non-salt hardness reduction and non-scaling techniques | [5 empty] | Total | 110645.3893 | 12600 | 35055 | 8000 | 12099.2 | 178399.5893
Task 1.1 | Develop protocol with stakeholders |  |  |  |  | by task | 15284.9004 | 4000 | 200 | 0 | 208.8
Task 1.2 | Test non-salt alternatives | [5 empty] | 91108.5513 | 8600 | 34855 | 8000 | 11681.6
Task 1.2A | Design and build test rig |  |  |  |  | subtask |  | 600 | 18450
Task 1.2B | Initial testing and modifications |  |  |  |  | subtask |  | 4000 | 2750
Task 1.2C | Field testing, season 1 |  |  |  |  | subtask |  | 0 | 4140 |  | 5840.8
Task 1.2D | Reporting |  |  |  |  | subtask |  | 0 | 0
Task 1.2E | Field testing, season 2 |  |  |  |  | subtask |  | 4000 | 9515 |  | 5840.8
Task 1.3 | Disseminate results | [5 empty] | 4251.9376 | 0 | 0 | 0 | 208.8
[7 empty] | Salary & Fringe | Contracts | Equip. & supplies | Capital | Travel | Total
Activity 2: Develop online tool for homeowners to reduce water softening salt | [6 empty] | 19969.9802 | 59000 | 400 | 0 | 0 | 79369.9802
Task 2.1 | Wireframe of online tool completed | [5 empty] | 11207.2758 | 15000 | 0 | 0 | 0
Task 2.2 | Online tool completed | [5 empty] | 6954.9188 | 35000 | 200 | 0 | 0
Task 2.3 | Tool is refined as needed base on feedback and results from Activity 1 | [5 empty] | 1807.7856 | 9000 | 200 | 0 | 0
[7 empty] | Salary & Fringe | Contracts | Equip. & supplies | Capital | Travel | Total
Activity 3: Community level chloride reduction strategies | [6 empty] | 54349.1837 | 50000 | 0 | 0 | 580 | 104929.1837
Task 3.1 | Identify two communities | [5 empty] | 8531.6174 | 0 | 0 | 0 | 116
Task 3.2 | Two communities implemented chloride reduction strategy | [5 empty] | 26309.7769 | 50000 | 0 | 0 | 232
Task 3.3 | Case studies completed and tools developed | [5 empty] | 19507.7894 | 0 | 0 | 0 | 232
Summary by staff type | [11 empty] | 362698.7531 | Total Direct
| Total funding | Total Salary/3 years | % | [8 empty] | 195857.3267 | Total Indirect
Sara | 33594.8164 | 258206.34 | 13.0108
Jeff | 9373.4037 | 329035.2 | 2.8488
Researchers | 132519.1248 | 142672.608 | 92.8834
Student | 7802.9769 | 72758.4 | 10.7245
Editor | 1674.2314 | 133099.2 | 1.2579
184964.5531
could use FY 2022 rate

## Activity 1 (hidden)
SAFL Assumptions:
Project: | LCCMR_Sara Heger et al |  |  | start | end |  |  |  |  | Task 1.1 is in FY 2021
Budget by: M. Hernick et al |  |  | Project dates | 2020-07-01 | 2023-06-30 |  |  |  |  | Assume Task 1.2 is all FY 2022 (actually part 21, all of 22, part 23)
Date: | 2019-04-04 | [8 empty] | Task 1.3 is in FY 2023
[10 empty] | Assume fringe is same as 2019, mileage .58 | [5 empty] | TASK ADDED 3/11/2019
[10 empty] | Assume 3% per year (match WRC) | [21 empty] | 07/01/2020 - 06/30/2021 |  |  |  |  | 07/01/2021 - 06/30/2022 |  |  | 07/01/2022 - 06/30/2023
[10 empty] | FTE = | 2080 | hours/year
Activity 1 | Activity 1: Test non-salt hardness reduction and non-scaling techniques
|  |  | FY 2021 |  |  | FY 2022 | [11 empty] | FY 2022 |  | FY 2023 | [10 empty] | FY 2019 hourly | FY21 Hourly Amount | FY21 Hourly Fringe | Fringe Rate | FY21 Annual Salary | FY21 Annual Fringe | FY22 hourly with 3% increase | FY22 Annual Salary | FY22 Annual Fringe | FY23 hourly with 3% increase | FY23 Annual Salary | FY 23 Annual Fringe
[8 empty] | Design and build test rig |  | Initial testing and modifications |  | Field testing, season 1 |  | Reporting |  | Field testing, season 2
[6 empty] | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 Summary | [5 empty] | Activity 1 | [5 empty] | Sara Heger |  | 41.3792 | 14.8965 | 36% | 86068.78 | 30984.7608 | 42.6206 | 88650.8434 | 31914.3036 | 43.8992 | 91310.3653 | 32871.7315
|  |  | $/hr | Task 1.1 |  |  |  | Task 1.2A |  | Task 1.2B |  | Task 1.2C |  | Task 1.2D |  | Task 1.2E |  | Task 1.2 |  | Task 1.3 |  | Task 1.3 |  | TOTAL | [5 empty] | WRC Staff |  | 21.01 | 6.198 | 29.5% | 43700.8 | 12891.736 | 21.6403 | 45011.824 | 13278.4881 | 22.2895 | 46362.1787 | 13676.8427
Salary |  |  | rate | hours | cost | Staff | rate | hours | cost | hours | cost | hours | cost | hours | cost | hours | cost | hours | cost | Staff | rate | hours | cost | hours | cost |  |  |  |  | WRC Editor |  | 21.3313 | 6.2927 | 29.5% | 38822.966 | 11452.775 | 21.9712 | 39987.655 | 11796.3582 | 22.6304 | 41187.2846 | 12150.249
| Jeff Marr | Engineer | 55.8938 | 20 | 1117.876 | Jeff Marr | 57.5706 | 20 | 1151.4123 | 0 | 0 | 20 | 1151.4123 | 30 | 1727.1184 | 20 | 1151.4123 | 90 | 5181.3553 | Jeff Marr | 59.2977 | 10 | 592.9773 | 120 | 6892.2086
| Matt Hernick | Engineer | 30.5068 | 100 | 3050.68 | Matt Hernick | 31.422 | 240 | 7541.281 | 60 | 1885.3202 | 120 | 3770.6405 | 120 | 3770.6405 | 140 | 4399.0806 | 680 | 21366.9627 | Matt Hernick | 32.3647 | 30 | 970.9399 | 810 | 25388.5826
| Aaron Ketchmark | Scientist | 22.8642 | 60 | 1371.852 | Aaron Ketchmark | 23.5501 | 280 | 6594.0353 | 120 | 2826.0151 | 300 | 7065.0378 | 60 | 1413.0076 | 320 | 7536.0403 | 1080 | 25434.1361 | Aaron Ketchmark | 24.2566 | 0 | 0 | 1140 | 26805.9881
| Jim Tucker | Scientist | 33.4536 | 0 | 0 | Jim Tucker | 34.4572 | 120 | 4134.865 | 40 | 1378.2883 | 80 | 2756.5766 | 0 | 0 | 80 | 2756.5766 | 320 | 11026.3066 | Jim Tucker | 35.4909 | 0 | 0 | 320 | 11026.3066
| SAFL Undergrad | Student | 11.66 | 20 | 233.2 | SAFL Undergrad | 12.0098 | 80 | 960.784 | 40 | 480.392 | 200 | 2401.96 | 60 | 720.588 | 240 | 2882.352 | 620 | 7446.076 | SAFL Undergrad | 12.3701 | 10 | 123.7009 | 650 | 7802.9769
| Sara Heger | Professior | 41.3792 | 100 | 4137.9221 | Sara Heger | 42.6206 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 213.103 | 20 | 852.412 | 25 | 1065.5149 | Sara Heger | 43.8992 | 20 | 877.9843 | 145 | 6081.4213
| WRC Staff | Scientist | 21.01 | 80 | 1680.8 | WRC Staff | 21.6403 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 108.2015 | 5 | 108.2015 | 10 | 216.403 | WRC Staff | 22.2895 | 20 | 445.7902 | 110 | 2342.9932
| WRC Editor | Editor | 21.3313 | 0 | 0 | WRC Editor | 21.9712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | WRC Editor | 22.6304 | 10 | 226.3038 | 10 | 226.3038
[24 empty] | Subtotal Salary | 86566.7811 |  | Summary per person
Fringe |  |  | Fringe % |  |  | rate: Fringe % |  | Fringe % | [5 empty] | Sal + frg | % FTE over 3 years |  | Research Scientists
| Jeff Marr |  | 36% |  | 402.4354 | rate: 36%; Task 1.2A cost: 414.5084; Task 1.2B cost: 0; Task 1.2C cost: 414.5084; Task 1.2D cost: 621.7626; Task 1.2E cost: 414.5084; Task 1.2 cost: 1865.2879 |  | 36% |  | 213.4718 |  | 2481.1951 |  | 9373.4037 | 1.923% | Jeff Marr
| Matt Hernick |  | 29.5% |  | 899.9506 | rate: 29.5%; Task 1.2A cost: 2224.6779; Task 1.2B cost: 556.1695; Task 1.2C cost: 1112.3389; Task 1.2D cost: 1112.3389; Task 1.2E cost: 1297.7288; Task 1.2 cost: 6303.254 |  | 29.5% |  | 286.4273 |  | 7489.6319 |  | 32878.2145 | 12.98% | Matt Hernick | 84905.2123 | 38.14%
| Aaron Ketchmark |  | 29.5% |  | 404.6963 | rate: 29.5%; Task 1.2A cost: 1945.2404; Task 1.2B cost: 833.6745; Task 1.2C cost: 2084.1862; Task 1.2D cost: 416.8372; Task 1.2E cost: 2223.1319; Task 1.2 cost: 7503.0701 |  | 29.5% |  | 0 |  | 7907.7665 |  | 34713.7546 | 18.27% | Aaron Ketchmark
| Jim Tucker |  | 29.5% |  | 0 | rate: 29.5%; Task 1.2A cost: 1219.7852; Task 1.2B cost: 406.5951; Task 1.2C cost: 813.1901; Task 1.2D cost: 0; Task 1.2E cost: 813.1901; Task 1.2 cost: 3252.7604 |  | 29.5% |  | 0 |  | 3252.7604 |  | 14279.067 | 5.128% | Jim Tucker
| SAFL Undergrad |  | 0% |  | 0 | rate: 0%; Task 1.2A cost: 0; Task 1.2B cost: 0; Task 1.2C cost: 0; Task 1.2D cost: 0; Task 1.2E cost: 0; Task 1.2 cost: 0 |  | 0% |  | 0 |  | 0 |  | 7802.9769 | 10.42% | SAFL Undergrad
| Sara Heger |  | 36% |  | 1489.652 | rate: 36%; Task 1.2A cost: 0; Task 1.2B cost: 0; Task 1.2C cost: 0; Task 1.2D cost: 76.7171; Task 1.2E cost: 306.8683; Task 1.2 cost: 383.5854 |  | 36% |  | 316.0743 |  | 2189.3117 |  | 8270.733 | 2.324% | Sara Heger
| WRC Staff |  | 29.5% |  | 495.836 | rate: 29.5%; Task 1.2A cost: 0; Task 1.2B cost: 0; Task 1.2C cost: 0; Task 1.2D cost: 31.9194; Task 1.2E cost: 31.9194; Task 1.2 cost: 63.8389 |  | 29.5% |  | 131.5081 |  | 691.183 |  | 3034.1762 | 1.763% | WRC Staff
| WRC Editor |  | 29.5% |  | 0 | rate: 29.5%; Task 1.2A cost: 0; Task 1.2B cost: 0; Task 1.2C cost: 0; Task 1.2D cost: 0; Task 1.2E cost: 0; Task 1.2 cost: 0 |  | 29.5% |  | 66.7596 |  | 66.7596 |  | 293.0634 | 0.1603% | WRC Editor
[24 empty] | Subtotal Fringe | 24078.6082
[5 empty] | 15284.9004 | Task 1.2A cost: 26186.5894; Task 1.2B cost: 8366.4547; Task 1.2C cost: 21569.8508; Task 1.2D cost: 10212.2343; Task 1.2E cost: 24773.4222; Task 1.2 cost: 91108.5513 |  |  |  | 4251.9376 | Total Salary and Fringe | 110645.3893
Professional/Technical/Service Contracts | [5 empty] | Task 1.2A cost: 0; Task 1.2B cost: 0; Task 1.2C cost: 0; Task 1.2D cost: 0; Task 1.2E cost: 0; Task 1.2 cost: 0 |  |  |  | 0 |  | 4000
| Fortin |  |  |  | 4000 | Task 1.2B cost: $50 per samp x 4 device x 4 samp x 5 sites; Task 1.2 cost: 0 | [5 empty] | 0
| Developer |  |  |  |  | Task 1.2A cost: 600; Task 1.2B cost: 4000; Task 1.2E cost: 4000; Task 1.2 cost: 8600 | [5 empty] | 8600 | for outside lab chemical testing
| Water Quality Lab |  |  |  |  | Task 1.2 cost: 0
[5 empty] | 4000 | Task 1.2A cost: 600; Task 1.2B cost: 4000; Task 1.2C cost: 0; Task 1.2D cost: 0; Task 1.2E cost: 4000; Task 1.2 cost: 8600 |  |  |  | 0 | Total Service Contracts | 12600
Equipment, Tools and Supplies | [19 empty] | Text for Template
| Treatment systems |  |  |  |  | Task 1.2A hours: Treatment devices; Task 1.2A cost: 4000; Task 1.2E hours: Treatment devices; Task 1.2E cost: 3500; Task 1.2 cost: 7500 | Salt-free alternative water conditioning systems
| Plumbing, water heating and electrical |  |  |  |  | Task 1.2A hours: Plumbing; Task 1.2A cost: 3000; Task 1.2B hours: Plumb mod; Task 1.2B cost: 500; Task 1.2E hours: plumb 2nd seas; Task 1.2E cost: 1000; Task 1.2 cost: 9000 | Mobile test unit plumbing, water heating and electrical
[8 empty] | Electrical | 1500 | Elect mod | 500 |  |  |  |  | elec 2nd seaso | 1000
[8 empty] | Wtr Heating | 1500
| Furnishing, signage, safety equip. |  |  |  |  | Task 1.2A hours: Furnishing; Task 1.2A cost: 1200; Task 1.2 cost: 3700 | Mobile test unit furnishing, signage, safety equip.
[8 empty] | Signage | 2500
| Maintenance, repairs, modifications |  |  |  |  | Task 1.2C hours: Maint. and storage; Task 1.2C cost: 1900; Task 1.2E hours: Maint. 2nd season; Task 1.2E cost: 1500; Task 1.2 cost: 3900 | Mobile test unit maintenance, repairs, modifications
[16 empty] | Decommission trlr | 500
| Control and data system, remote communication | [6 empty] | Control & data system | 4000 | Data mod | 500 | Remote communications | 240 |  |  | Remote communications | 240 |  | 4980 | Mobile test unit control and data system, remote communication
| Water tests, chemicals, supplies |  |  | Literature | 200 |  |  | Supplies | 750 | Test kits | 750 | Chemicals (HNO3, ) | 500 |  |  | Chemicals (HNO3, ) | 500 |  | 5975 | Chemicals, water test kits, supplies | [5 empty] | for onboard/simple chemical testing
[10 empty] | Chemicals (HNO3, ) | 500 | Supplies | 1500 |  |  | Supplies | 1275
Capital Expenditures Over $5,000 |  |  |  |  | 200 | Task 1.2A cost: 18450; Task 1.2B cost: 2750; Task 1.2C cost: 4140; Task 1.2D cost: 0; Task 1.2E cost: 9515; Task 1.2 cost: 35055 |  |  |  | 0 | Subtotal Supplies | 35055
[8 empty] | Trailer - capital | 8000 | [9 empty] | 8000
0
0
Travel in Minnesota |  |  | rate |  | 0 | Task 1.2A cost: 8000; Task 1.2B cost: 0; Task 1.2C cost: 0; Task 1.2D cost: 0; Task 1.2E cost: 0; Task 1.2 hours: totals; Task 1.2 cost: 8000 |  |  |  | 0 | Subtotal Capital Exp. | 8000 |  | Total miles |  |  | Total hotel nights
|  | Mileage - car | 0.58 | 360 | 208.8 |  |  |  | 0 |  | 0 | 1760 | 1020.8 |  | 0 | 1760 | 1020.8 | 3520 | 2041.6 |  |  | 360 | 208.8 |  | 2459.2 |  | 4240 |  |  | 16
|  | per diem | 41.25 |  |  | Task 1.2C hours: 16; Task 1.2C cost: 660; Task 1.2E hours: 16; Task 1.2E cost: 660; Task 1.2 hours: 32; Task 1.2 cost: 1320 | [5 empty] | 2640
|  | Lodging | 80 |  |  | Task 1.2C hours: 8; Task 1.2C cost: 640; Task 1.2E hours: 8; Task 1.2E cost: 640; Task 1.2 hours: 16; Task 1.2 cost: 1280 | [5 empty] | 1280
|  | Tow vehicle per mile | 1 |  |  | Task 1.2C hours: 3520; Task 1.2C cost: 3520; Task 1.2E hours: 3520; Task 1.2E cost: 3520; Task 1.2 hours: 7040; Task 1.2 cost: 7040 | [5 empty] | 7040
[5 empty] | 208.8 | Task 1.2A cost: 0; Task 1.2B cost: 0; Task 1.2C cost: 5840.8; Task 1.2D cost: 0; Task 1.2E cost: 5840.8; Task 1.2 cost: 11681.6 |  |  |  | 208.8 | Subtotal Travel | 12099.2
[8 empty] | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 | Task 1.2 Summary
[5 empty] | 19693.7004 | Task 1.2A cost: 53236.5894; Task 1.2B cost: 15116.4547; Task 1.2C hours: total; Task 1.2C cost: 31550.6508; Task 1.2D cost: 10212.2343; Task 1.2E cost: 44129.2222; Task 1.2 cost: 154445.1513 |  |  |  | 4460.7376
[6 empty] | Task 1.2C hours: per site (5); Task 1.2C cost: 6310.1302; Task 1.2E hours: per site (5); Task 1.2E cost: 8825.8444 |  |  |  |  | Activity 1
[6 empty] | Task 1.2A hours: Trailer 7x16x7 high |  |  |  |  | Total Direct | 178399.5893
[6 empty] | Task 1.2D hours: Reporting: |  |  |  |  | Total Indirect 54% | 112391.7412 | (Match)
Initial methods report
Brief data summary after each site
Season end summary and initial recommendation
[12 empty] | Travel - assume five sites outstate |  |  |  | second season
similar to first (5 sites)
[12 empty] | Deploy +/- one month each, June - October |  |  |  | add some time for startup
[12 empty] | Prep trailer at lab, travel to site, set up, start test |  |  |  | and cost for repair/enhancements
[12 empty] | Assume an overnight is required for 4 of 5 |  |  |  | could also be used for new techs
Probably one intermediate trip
At end of test, clean up, similar to start up
Haul trailer to next site (back to lab assumed)
Mileage
[12 empty] | Five sites | 130
170
390
150
40
[12 empty] | total | 880
[12 empty] | car visit | 1760 | Small vehicle one trip per site - pay mileage rate of 0.58
[12 empty] | 4x (out-back x 2) | 3520 | Tow vehicle 2 trips per site
[12 empty] | assume 2 hotel nights per site |  | (one per trip)
Tow vehicle - fleet rental
$51/day + .40/mile
[12 empty] | 2428 | based on miles above
But, say $1 per mile for towing
Text for template
Activity 1 - 3,520 miles at $0.58/mile for 10 outstate sites ($2,042), 7,040 miles at $1/mile tow vehicle for mobile test trailer ($7,040), 16 hotel nights @ $80/night ($1,280), and 32 first/last day per diem @$41.25 ($1,320)

## Activity 2 (hidden)
Project: | LCCMR_Sara Heger et al |  |  | start | end
Budget by: |  |  | Project dates | 2020-07-01 | 2022-06-30
Date: | 2019-03-05
Activity 2 | Activity 2: Develop online tool for homeowners to reduce water softening salt
[6 empty] | Task 1.2 | Task 1.2 |  |  | Activity 2 |  |  |  |  | 07/01/2020 - 06/30/2021 |  |  |  |  | 07/01/2021 - 06/30/2022 |  |  | 07/01/2022 - 06/30/2023
|  |  | Hourly Rate | Task 2.1 |  | Task 2.2 |  | Task 2.3 |  | TOTAL |  |  | Summary per person |  | FY21 Hourly Amount | FY21 Hourly Fringe | Fringe Rate | FY21 Annual Salary | FY21 Annual Fringe | FY22 hourly with 3% increase | FY22 Annual Salary | FY22 Annual Fringe | FY23 hourly with 3% increase | FY23 Annual Salary | FY 23 Annual Fringe
Salary |  |  | ($/hr) | hours | cost | hours | cost | hours | cost | hours | cost |  | 11255.1482 | Sara Heger | 41.3792 | 14.8965 | 36% | 86068.78 | 30984.7608 | 42.6206 | 88650.8434 | 31914.3036 | 43.8992 | 91310.3653 | 32871.7315
| Sara Heger | Professior | 41.3792 | 100 | 4137.9221 | 80 | 3310.3377 | 20 | 827.5844 | 200 | 8275.8442 |  | 8162.385 | WRC Staff | 21.01 | 6.198 | 29.5% | 43700.8 | 12891.736 | 21.6403 | 45011.824 | 13278.4881 | 22.2895 | 46362.1787 | 13676.8427
| WRC Staff | Scientist | 21.01 | 200 | 4202 | 80 | 1680.8 | 20 | 420.2 | 300 | 6303 |  | 552.447 | WRC Editor | 21.9699 | 6.4811 | 29.5% | 39985.218 | 11795.6393 | 22.629 | 41184.7745 | 12149.5085 | 23.3079 | 42420.3178 | 12513.9937
| WRC Editor | Editor | 21.33 | 5 | 106.65 | 10 | 213.3 | 5 | 106.65 | 20 | 426.6
[10 empty] | Subotal Salary | 15005.4442
Fringe
| Sara Heger |  | 36% |  | 1489.652 |  | 1191.7216 |  | 297.9304 |  | 2979.3039
| WRC Staff |  | 29.5% |  | 1239.59 |  | 495.836 |  | 123.959 |  | 1859.385
| WRC Editor |  | 29.5% |  | 31.4617 |  | 62.9235 |  | 31.4617 |  | 125.847
[10 empty] | Subtotal Fringe | 4964.5359
[5 empty] | 11207.2758 |  | 6954.9188 |  | 1807.7856 | Total Salary and Fringe | 19969.9802
Professional/Technical/Service Contracts
| Fortin |  |  |  | 5000 |  | 7000 |  | 2000 |  | 14000
| Developer |  |  |  | 10000 |  | 28000 |  | 7000 |  | 45000
[5 empty] | 15000 |  | 35000 |  | 9000 | Total Service Contracts | 59000
Equipment, Tools and Supplies |  |  |  |  | 200
| Software | [5 empty] | 200 |  | 200
Domain Fee
[5 empty] | 0 |  | 200 |  | 200 | Subtotal Supplies | 400
Travel in Minnesota |  | Mileage |  |  | 0 |  | 0 |  | 0
Lodging
[5 empty] | 0 |  | 0 |  | 0 | Subtotal Travel | 0
[5 empty] | 26207.2758 |  | 42154.9188 |  | 11007.7856
Activity 2
[10 empty] | Total Direct | 79369.9802
[10 empty] | Total Indirect | 42859.7893 | (match)

## Actvity3 (hidden)
Project: | LCCMR_Sara Heger et al |  |  | start | end
Budget by: |  |  | Project dates | 2020-07-01 | 2022-06-30
Date: | 2019-04-08
Activity 2 | Activity 2: Assist Communities | [12 empty] | 07/01/2020 - 06/30/2021 |  |  |  |  | 07/01/2021 - 06/30/2022 |  |  | 07/01/2022 - 06/30/2023
[14 empty] | FY21 Hourly Amount | FY21 Hourly Fringe | Fringe Rate | FY21 Annual Salary | FY21 Annual Fringe | FY22 hourly with 3% increase | FY22 Annual Salary | FY22 Annual Fringe | FY23 hourly with 3% increase | FY23 Annual Salary | FY 23 Annual Fringe
[6 empty] | Task 1.2 | Task 1.2 |  |  | Activity 2 |  |  | Sara Heger | 41.3792 | 14.8965 | 36% | 86068.78 | 30984.7608 | 42.6206 | 88650.8434 | 31914.3036 | 43.8992 | 91310.3653 | 32871.7315
|  |  | Hourly Rate | Task 2.1 |  | Task 2.2 |  | Task 2.3 |  | TOTAL |  |  | WRC Staff | 21.01 | 6.198 | 29.5% | 43700.8 | 12891.736 | 21.6403 | 45011.824 | 13278.4881 | 22.2895 | 46362.1787 | 13676.8427
Salary |  |  | ($/hr) | hours | cost | hours | cost | hours | cost | hours | cost |  | WRC Editor | 21.3313 | 6.2927 | 29.5% | 38822.966 | 11452.775 | 21.9712 | 39987.655 | 11796.3582 | 22.6304 | 41187.2846 | 12150.249
| Jeff Marr | Engineer | 55.8938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Matt Hernick | Engineer | 30.5068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Aaron Ketchmark | Scientist | 22.842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Jim Tucker | Scientist | 33.4536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SAFL Undergrad | Student | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sara Heger | Professior | 41.3792 | 50 | 2068.9611 | 100 | 4137.9221 | 100 | 4137.9221 | 250 | 10344.8053
| WRC Staff | Scientist | 21.01 | 200 | 4202 | 750 | 15757.5 | 500 | 10505 | 1450 | 30464.5
| WRC Editor | Editor | 21.3313 | 10 | 213.313 | 10 | 213.313 | 10 | 213.313 | 30 | 639.939
[10 empty] | Subtotal Salary | 41449.2443
Fringe | [11 empty] | Summary per person
| Jeff Marr |  | 36% |  | 0 |  | 0 |  | 0 |  | 0
| Matt Hernick |  | 29.5% |  | 0 |  | 0 |  | 0 |  | 0
| Aaron Ketchmark |  | 29.5% |  | 0 |  | 0 |  | 0 |  | 0
| Jim Tucker |  | 29.5% |  | 0 |  | 0 |  | 0 |  | 0
| SAFL Undergrad |  | 0% |  | 0 |  | 0 |  | 0 |  | 0
| Sara Heger |  | 36% |  | 744.826 |  | 1489.652 |  | 1489.652 |  | 3724.1299 | 14068.9352
| WRC Staff | Scientist | 29.5% |  | 1239.59 |  | 4648.4625 |  | 3098.975 |  | 8987.0275 | 39451.5275
| WRC Editor | Editor | 29.5% |  | 62.9273 |  | 62.9273 |  | 62.9273 | 8.85 | 188.782 | 828.721
[10 empty] | Subtotal Fringe | 12899.9394
[5 empty] | 8531.6174 |  | 26309.7769 |  | 19507.7894 | Total Salary and Fringe | 54349.1837
Equipment | [6 empty] | 50000 |  |  |  | 50000
0
[5 empty] | 0 |  | 50000 |  | 0 | Total Service Contracts | 50000
Travel in Minnesota |  | Mileage | 0.58 | 200 | 116 | 400 | 232 | 400 | 232
[5 empty] | 116 |  | 232 |  | 232 | Subtotal Travel | 580
[10 empty] | Total Direct | 104929.1837
[10 empty] | Total Indirect | 56661.7592

## SAFLrates (hidden)
USED FOR SPONSORED PROJECTS
|  |  | FY 2019 - actual | [9 empty] | FY21 Rates with 3% increase per year
| Emplid/ Account | Dept ID | hrly rate | Fringe Class | frg | Total | With IDC | base |  | Fringe rates: |  |  |  | FY21 hrly rate with 6% increase | hrly fringe rate | Fringe Class | FY20 Fringe Rate | Total Hourly | FY21 Annual base | FY21 Fringe | FY22 hourly Rate with 3% increase | FY22 Annual Base 3% increase | FY22 Annual Fringe | FY23 hourly rate with 3% increase | FY23 Annual Base 3% increase | FY 23 Annual Fringe
Arnold, Patrick | 3573878/700501 | 11107 | 29.92 | Civil Service | 8.5 | 38.42 | 59.17 | 62234 | Arnold, Patrick | Faculty/acad | 34.2% |  | Arnold, Patrick | 31.7152 | 9.356 | Civil Service | 29.5% | 41.0712 | 65967.616 | 19460.4467 | 32.6667 | 67946.6445 | 20044.2601 | 33.6467 | 69985.0438 | 20645.5879
Christopher, Richard | 1279412/700201 | 11107 | 32.82 | Faculty/acad | 11.22 | 44.04 | 67.82 | 68266 | Christopher, Richard | Civil Service | 28.4% |  | Christopher, Richard | 34.7892 | 12.5241 | Faculty/acad | 36% | 47.3133 | 72361.536 | 26050.153 | 35.8329 | 74532.3821 | 26831.6575 | 36.9079 | 76768.3535 | 27636.6073
Ellis, Chris |  |  |  | Temp/casual |  |  |  |  | Ellis, Chris | Temp/casual | 7.7% |  | Ellis, Chris | 0 |  | Temp/casual | 8.2% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Erickson, Andy | 1883998/700201 | 11107 | 33.87 | Faculty/acad | 11.58 | 45.45 | 69.99 | 70450 | Erickson, Andy | Post docs | 23% |  | Erickson, Andy | 35.9022 | 12.9248 | Faculty/acad | 36% | 48.827 | 74676.576 | 26883.5674 | 36.9793 | 76916.8733 | 27690.0744 | 38.0886 | 79224.3795 | 28520.7766
Erickson, Ben | 1195666/700501 | 11107 | 29.63 | Civil Service | 8.41 | 38.04 | 58.58 | 61630 | Erickson, Ben | Grad students | 17.7% | *health component only | Erickson, Ben | 31.4078 | 9.2653 | Civil Service | 29.5% | 40.6731 | 65328.224 | 19271.8261 | 32.35 | 67288.0707 | 19849.9809 | 33.3205 | 69306.7128 | 20445.4803
Feist, Chris | 3673604/700501 | 11107 | 27.2 | Civil Service | 7.72 | 34.92 | 53.78 | 56576 | Feist, Chris | Undergrads | 0% |  | Feist, Chris | 28.832 | 8.5054 | Civil Service | 29.5% | 37.3374 | 59970.56 | 17691.3152 | 29.697 | 61769.6768 | 18222.0547 | 30.5879 | 63622.7671 | 18768.7163
Gabrielson, Rob | 3760653/700501 | 11107 | 21.08 | Civil Service | 5.99 | 27.07 | 41.69 | 43846 | Gabrielson, Rob |  |  |  | Gabrielson, Rob | 22.3448 | 6.5917 | Civil Service | 29.5% | 28.9365 | 46477.184 | 13710.7693 | 23.0151 | 47871.4995 | 14122.0924 | 23.7056 | 49307.6445 | 14545.7551
Heitkamp, Barbara | 4588165/700501 | 11107 | 30.01 | Civil Service | 8.52 | 38.53 | 59.34 | 62421 | Heitkamp, Barbara |  |  |  | Heitkamp, Barbara | 31.8106 | 9.3841 | Civil Service | 29.5% | 41.1947 | 66166.048 | 19518.9842 | 32.7649 | 68151.0294 | 20104.5537 | 33.7479 | 70195.5603 | 20707.6903
Hernick, Matt | 2668505/700501 | 11107 | 28.78 | Civil Service | 8.17 | 36.95 | 56.9 | 59862 | Hernick, Matt |  |  |  | Hernick, Matt | 30.5068 | 8.9995 | Civil Service | 29.5% | 39.5063 | 63454.144 | 18718.9725 | 31.422 | 65357.7683 | 19280.5417 | 32.3647 | 67318.5014 | 19858.9579
Ketchmark, Aaron | 3915777/700501 | 11107 | 21.57 | Civil Service | 6.13 | 27.7 | 42.66 | 44866 | Ketchmark, Aaron |  |  |  | Ketchmark, Aaron | 22.8642 | 6.7449 | Civil Service | 29.5% | 29.6091 | 47557.536 | 14029.4731 | 23.5501 | 48984.2621 | 14450.3573 | 24.2566 | 50453.7899 | 14883.868
Kozarek, Jess | 4362656/700201 | 11107 | 34.09 | Faculty/acad | 11.66 | 45.75 | 70.46 | 70907 | Kozarek, Jess |  |  |  | Kozarek, Jess | 36.1354 | 13.0087 | Faculty/acad | 36% | 49.1441 | 75161.632 | 27058.1875 | 37.2195 | 77416.481 | 27869.9331 | 38.336 | 79738.9754 | 28706.0311
Lueker, Matthew | 2279336/700501 | 11107 | 28.52 | Civil Service | 8.1 | 36.62 | 56.39 | 59322 | Lueker, Matthew |  |  |  | Lueker, Matthew | 30.2312 | 8.9182 | Civil Service | 29.5% | 39.1494 | 62880.896 | 18549.8643 | 31.1381 | 64767.3229 | 19106.3602 | 32.0723 | 66710.3426 | 19679.5511
Marr, Jeff | 1558686/700202 | 11107 | 52.73 | Faculty/acad | 18.03 | 70.76 | 108.97 | 109678 | Marr, Jeff |  |  |  | Marr, Jeff | 55.8938 | 20.1218 | Faculty/acad | 36% | 76.0156 | 116259.104 | 41853.2774 | 57.5706 | 119746.8771 | 43108.8758 | 59.2977 | 123339.2834 | 44402.142
Marttinen, Dale | 4009228/700501 | 11107 | 21.31 | Civil Service | 6.05 | 27.36 | 42.13 | 44325 | Marttinen, Dale |  |  |  | Marttinen, Dale | 22.5886 | 6.6636 | Civil Service | 29.5% | 29.2522 | 46984.288 | 13860.365 | 23.2663 | 48393.8166 | 14276.1759 | 23.9642 | 49845.6311 | 14704.4612
Milliren, Chris | 3693048/700501 | 11107 | 25.4 | Civil Service | 7.21 | 32.61 | 50.22 | 52832 | Milliren, Chris |  |  |  | Milliren, Chris | 26.924 | 7.9426 | Civil Service | 29.5% | 34.8666 | 56001.92 | 16520.5664 | 27.7317 | 57681.9776 | 17016.1834 | 28.5637 | 59412.4369 | 17526.6689
Mullin, James | 2108398/700531 | 11107 | 41.8 | Temp/casual | 3.22 | 45.02 | 69.33 | 86944 | Mullin, James |  |  |  | Mullin, James | 44.308 | 0 | Temp/casual |  | 44.308 | 92160.64 | 0 | 45.6372 | 94925.4592 | 0 | 47.0064 | 97773.223 | 0
Steen, Erik | 2610287/700501 | 11107 | 26.38 | Civil Service | 7.49 | 33.87 | 52.16 | 54870 | Steen, Erik |  |  |  | Steen, Erik | 27.9628 | 8.249 | Civil Service | 29.5% | 36.2118 | 58162.624 | 17157.9741 | 28.8017 | 59907.5027 | 17672.7133 | 29.6657 | 61704.7278 | 18202.8947
Student |  |  | 11 | Undergrads | 0 | 11 | 16.94 | 22880 | Student |  |  |  | Student | 11.66 | 0 | Undergrads | 0% | 11.66 | 24252.8 | 0 | 12.0098 | 24980.384 | 0 | 12.3701 | 25729.7955 | 0
Tucker, James (50% appt) | 1340794/700501 | 11107 | 31.56 | Civil Service | 8.96 | 40.52 | 62.4 | 32822 | Tucker, James (50% appt) |  |  |  | Tucker, James (50% appt) | 33.4536 | 9.8688 | Civil Service | 29.5% | 43.3224 | 69583.488 | 20527.129 | 34.4572 | 71670.9926 | 21142.9428 | 35.4909 | 73821.1224 | 21777.2311
Overhead Rate = FY19 |  |  | 54%

## Project Budget_template
Attachment A: Project Budget Spreadsheet
Environment and Natural Resources Trust Fund
M.L. 2020 Budget Spreadsheet
Legal Citation:
Project Manager: Dr. Sara Heger
Project Title: Reducing Chloride in Minnesota’s Water from Water Softening
Organization: University of Minnesota
Project Budget: $362,699
Project Length and Completion Date: 3 years, 6/30/23
Today's Date: 4/8/19
ENVIRONMENT AND NATURAL RESOURCES TRUST FUND BUDGET |  | Budget | Amount Spent | Balance
BUDGET ITEM
Personnel (Wages and Benefits) |  | 184964.5531 | 0
Dr. Sara Heger/Project PI, $33,595 (64% salary, 36% benefits), 9.3% FTE each year for 3 of years
Jeff Marr/Engineer, $9,373 (64% salary, 36% benefits), 1.9% FTE each year for 3 of years
4 - Research Scientists, $132,519 (70.5% salary, 29.5% benefits), 3 years - WRC Reseacher $50,649, 29% FTE for 3 years, SAFL Researcher $32,878, 13% FTE for 3 years, SAFL Researcher $34,713 18% FTE for 3 years , SAFL Researcher $14,279, 5% FTE for 3 years
Student Worker, $7,803 (100% salary), 10.7% per year for 3 years
Editor, $1,674, (70.5% salary, 29.5% benefits), 1% FTE for 3 years ( $1,292.66 salary + $381.33 benefits)
Professional/Technical/Service Contracts
Fortin Consulting will provide expertise related to tool development and softening alternatives through a sole source contract following UMN policies (futher documentation could be provided if needed). |  | 18000 | 0
Tool development expert with be hired through a completive bid process following UMN Policies. |  | 45000 | 0
Contract lab to analyze water quality samples hired through UMN contracting. |  | 8600
Equipment/Tools/Supplies
Salt-free alternative water conditioning systems |  | 7500 | 0
Mobile test unit plumbing, water heating and electrical |  | 9000
Mobile test unit furnishing, signage, safety equip. |  | 3700
Mobile test unit maintenance, repairs, modifications |  | 3900
Mobile test unit control and data system, remote communication |  | 4980
Chemicals, water test kits, supplies |  | 5975
Software, domain fees |  | 400
Water softener replacement/rebate program removal in one of the two communities (50 homes at $1,000/ home) |  | 50000
Capital Expenditures Over $5,000
Enclosed trailer (approx. 7'x16') to build mobile test unit for salt-free softener alternatives |  | 8000 | 0
Fee Title Acquisition
|  | 0 | 0 | 0
Easement Acquisition
|  | 0 | 0 | 0
Professional Services for Acquisition
|  | 0 | 0 | 0
Printing
Travel expenses in Minnesota per UMN policy |  | 12679.2
Activity 1 - 3,520 miles at $0.58/mile for 10 outstate sites ($2,042), 7,040 miles at $1/mile tow vehicle for mobile test trailer ($7,040), 16 hotel nights @ $80/night ($1,280), and 32 first/last day per diem @$41.25 ($1,320)
Activity 3 - 1,000 miles to visit 2 communities at $0.58/mile ($580)
Other
|  | 0 | 0 | 0
COLUMN TOTAL |  | 362698.7531 | 0
SOURCE AND USE OF OTHER FUNDS CONTRIBUTED TO THE PROJECT | Status (secured or pending) | Budget | Spent | Balance
Non-State: Unrecovered UM Indirect at 54% minus capital equipment | pending | 191537 | 0 | 0
State: |  | 0 | 0 | 0
In kind:
Minnesota Pollution Control Agency, Brooke Asleson, Water Pollution Prevention Coordinator will provide expertise in development of tool and assist with community salt reduction strategies with 0.10 FTE over 3 years | Secured | 45000
Madison Metropolitan Sewerage District, Kathy Lake, Pollution Prevention Manager will provide expertise related to the water softener chloride reduction programs in place in Madison, WI. | Secured | 4500
Minnesota Water Quality Association, Scott Schiesser, President, Expertise in alternative testing protocol and online tool development | Secured | 6250
Other ENRTF APPROPRIATIONS AWARDED IN THE LAST SIX YEARS | Amount legally obligated but not yet spent | Budget | Spent | Balance
|  | 0 | 0 | 0