## Project Budget
Attachment A: Project Budget Spreadsheet
Environment and Natural Resources Trust Fund
M.L. 2020 Budget Spreadsheet
Legal Citation:
Project Manager: Dr. Peter Schultz
Project Title: LPF Urban Prairie and Stormwater Treatment Learning Lab
Organization: Longspur Prairie Fund
Project Budget: $62,943
Project Length and Completion Date: 2 years, 75 days; September 15, 2022
Today's Date: 11 March 2019
ENVIRONMENT AND NATURAL RESOURCES TRUST FUND BUDGET |  | Budget | Amount Spent | Balance
BUDGET ITEM
Personnel (Wages and Benefits) |  | 2540 | 0
Dr. Peter Schultz, Project Manager Duties: Oversight and management of project execution, management of professional contracts, and oversight of educational programmatic aspects. $1,540 (100% salary), (0.1FTE)
Cady Rutter, Administration and Logistics Duties: Execution and management of all organizational and project filings and administration, development of public educational programming, and communication with professional contractors. $1,000 (100% salary), (0.1FTE)
Professional/Technical/Service Contracts
Contract with Contour Design Studio is to be made for design services and construction administration services. Contour Design Studio was selected through a qualifications-based bid selection process. |  | 9996.75 | 0
Contract with a TBD contractor(s) is/are to be made by Contour Design Studio on behalf of the Longspur Prairie Fund for all pursuant miscellaneous costs of installations on proposed site, including: asphalt demolition and removal, curb modification, earthmoving and grading, parking lot re-striping, installation of underground stormwater pipe and infrastructure, and contingencies. TBD contractor(s) will be selected through a qualifications-based bid selection process. |  | 25707.5
Contract with Su Legatt of Legatt Design Services is to be made for liaison services with the City of Moorhead for all modifications and installations that require municipal approval and cooperation as the proposed site is city-owned land and includes a utilities box owned by Moorhead Public Services. Su Legatt was selected as a service contractor based on her qualifications and connections with City of Moorhead officials to execute the necessary communications. |  | 374
Equipment/Tools/Supplies
Hardscape: 6" Std. Concrete Curb and Gutter (qty. 30 LF), $900.00, Asphalt parking lot - 7" (qty 3,100 sq. ft.), $21,050.00 |  | 21050
Softscape: Seeding, native (qty 700 sq. ft.), $350.00, Plugs, native grass and forbs (qty 175), $875.00, Steel Edging (qty. 20 LF), $80.00, Rock Mulch (qty 23 sq. ft.), $70.00 |  | 1375
Site signage: Interpretive panels (qty 2), $800, Custom wrap for utility box on proposed site with installation (qty 1), $1,000.00 |  | 1800 | 0
Capital Expenditures Over $5,000
|  | 0 | 0 | 0
Fee Title Acquisition
|  | 0 | 0 | 0
Easement Acquisition
|  | 0 | 0 | 0
Professional Services for Acquisition
|  | 0 | 0 | 0
Printing
Educational Brochures and Packets |  | 100 | 0 | 100
Travel expenses in Minnesota
|  | 0 | 0 | 0
Other
|  | 0 | 0 | 0
COLUMN TOTAL |  | 62943.25 | 0 | 100
SOURCE AND USE OF OTHER FUNDS CONTRIBUTED TO THE PROJECT | Status (secured or pending) | Budget | Spent | Balance
Non-State: |  | 0 | 0 | 0
State: |  | 0 | 0 | 0
In kind: |  | 0 | 0 | 0
Other ENRTF APPROPRIATIONS AWARDED IN THE LAST SIX YEARS | Amount legally obligated but not yet spent | Budget | Spent | Balance
|  | 0 | 0 | 0