

**Environment and Natural Resources Trust Fund**

# 2021 Request for Proposal

## **General Information**

**Proposal ID:** 2021-100

**Proposal Title:** MN Backyard Science: Home-Based Environmental Education and Conservation

## **Project Manager Information**

**Name:** Christina Locke

**Organization:** U of MN, Humphrey School of Public Affairs

**Office Telephone:** (612) 625-6162

**Email:** clocke@umn.edu

## **Project Basic Information**

**Project Summary:** MN Backyard Science is a community-based environmental education program centered on native pollinator and plant conservation. Families participate from their own homes, and all program materials are publicly accessible.

**Funds Requested:** $502,000

**Proposed Project Completion:** 2024-06-30

**LCCMR Funding Category:** Environmental Education (C)

## **Project Location**

**What is the best scale for describing where your work will take place?** Statewide

**What is the best scale to describe the area impacted by your work?** Region(s): Metro

**When will the work impact occur?** During the Project and In the Future

## **Narrative**

**Describe the opportunity or problem your proposal seeks to address. Include any relevant background information.**

Environmental science literacy is necessary to build sustainable communities and promote citizen engagement in conservation issues. It is also an essential part of daily life: scientific literacy provides individuals with the knowledge and skills needed for decision making, participation in civic events, and essential skills for jobs in areas of science and technology. However, there is a gap in scientific literacy across income levels in Minnesota. In 2013, 39% of lower-income fifth graders were proficient in science compared to 74% of higher income fifth graders, and these gaps continued into high school and college readiness.
 Exposure to hands-on environmental education is key to fostering environmental science literacy in children, but informal, out-of-school educational experiences are rare in many low-income communities. Time and income constraints of low-income families can be barriers to participation in environmental programs for Minnesota children. Existing programs are typically short lived (e.g., a day trip to a museum), expensive (e.g., summer camp), and/or require significant travel (e.g., wilderness excursions). Local, low-cost, environmental science programs are needed to increase scientific literacy and broaden access to the world of conservation.

**What is your proposed solution to the problem or opportunity discussed above? i.e. What are you seeking funding to do? You will be asked to expand on this in Activities and Milestones.**

MN Backyard Science is a community-based, at-home educational project that introduces children to pollinator and plant conservation and provides vital resources for pollinators. The project has statewide and local components. The statewide component involves developing an online training portal with pollinator conservation information and educational materials for use by families across Minnesota. The local component involves partnering with 50 families in low-income areas of Minneapolis with children in grades 1-3. We will install a raised garden bed with pollinator friendly plants in the boulevard of each participating household. Participating families will attend a spring training session in person or online via Zoom to learn how to collect data on the plants and pollinators in their raised bed, and engage in at-home environmental science activities throughout the summer. This is an expansion of a successful pilot project we conducted in 2019 (citybackyardscience.org) with 12 households in Minneapolis. The pilot project attracted very high interest; we had to turn away over 100 interested families. In our survey of participants, 100% of respondents indicated that their children benefited from participating, and 70% indicated that their children became more observant of the natural world by participating.

**What are the specific project outcomes as they relate to the public purpose of protection, conservation, preservation, and enhancement of the state’s natural resources?**

MN Backyard Science encourages a conservation ethic in its participants, and provides vital resources for pollinators. By either engaging with the project team directly, or by taking advantage of free educational resources through our online portal, participants will:
1) increase engagement with and knowledge of the natural world, especially native plants and pollinators,
2) provide essential resources for pollinators, habitat for native insects, and increased stormwater filtration in boulevards, and
3) partake in free, at-home science activities that complement the Minnesota Department of Education science standards, which will increase students’ environmental, science, and conservation knowledge.

## **Activities and Milestones**

### **Activity 1: Community-based pollination science**

**Activity Budget:** $219,700

**Activity Description:**We will build and install 50 raised garden beds in previously grass-dominated boulevards (between the street and the sidewalk) in front of Minneapolis households. We will select participating households by partnering with three Minneapolis Public elementary schools where 1) more than 50% of 5th graders do not meet science standards of the Minnesota Comprehensive Assessment, and 2) most students live in Areas of Concentrated Poverty. We will work with teachers in those schools to identify families with children in grades 1-3 who wish to participate in MN Backyard Science. We will hire four high school students from these same communities as summer interns to assist with logistics, data collection, and engagement with participating families. Each participating household will be given a raised garden bed. Beds will be 60” x 30” x 12” high, constructed from high quality cedar lumber and planted with pollinator-friendly, low-maintenance native plants. Over the course of the growing season (May-Sept) across two years, families will observe pollinators visiting their beds, take measurements on flowering plants, and log data. Using the MN Department of Education science standards as a guide, we will create monthly activities for the students related to conservation, natural history, biodiversity, and math.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Select households | 2022-02-28 |
| Develop Year 1 educational activities | 2022-04-30 |
| Build and install garden beds | 2022-04-30 |
| Develop Year 2 educational activities | 2023-04-30 |
| Participants log data (plant and pollinator monitoring) and complete educational activities | 2023-09-30 |

### **Activity 2: Community training events and learning assessment**

**Activity Budget:** $187,000

**Activity Description:**We propose four community gatherings (two per year) to fulfill vital roles in this project: building relationships between researchers and participants, training participants, and assessing learning objectives. These events will occur in person and online via Zoom. We will convene with project participants before and after each growing season. The purpose of the first gathering is to introduce the project and train participants, while the second gathering is to share what we learned during the season and demonstrate each family’s contribution to the project overall. At each gathering, we will ask participants to complete a survey that we will use to assess learning outcomes. Our hypotheses are that scientific literacy of pollinators and ecology are higher, fear of bees is lower, and conservation is valued more highly after participating in the project compared to before. We will hire a graduate student researcher with expertise in educational evaluation techniques to develop and analyze the assessment to address these hypotheses. Results will be compiled into a research report detailing the learning outcomes of the project.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Develop learning assessment tool (pre-post survey) | 2022-03-31 |
| Develop training curricula | 2022-03-31 |
| Train participants on data collection protocol | 2022-04-30 |
| Wrap up season event for Year 1 | 2022-10-31 |
| Wrap up season event for Year 2 | 2023-10-31 |
| Analyze and report data from learning assessment | 2024-06-30 |

### **Activity 3: Online learning portal for public use**

**Activity Budget:** $95,300

**Activity Description:**We will develop a website (mnbackyardscience.org) that will host all educational resources developed by our team, as well as detailed plans on how households can construct and plant their own MN Backyard Science beds. This website will result in two primary outcomes: 1) a centralized resource for education, information, and training for the 50 households involved in the local component of the project, and 2) detailed tutorials that will allow any Minnesotan to participate in this home-based environmental education and conservation initiative. We will hire a web developer to help us create a website that is comprehensive and easy to use with rich, interactive content (e.g., pollinator identification tutorials and games). Households will also use this website to upload pollinator and plant data collected at their bed, enabling us to track pollinator visitation and generate valuable data on pollinator communities and visitation rates across the state. These data will be shared with Minnesota conservation groups and scientists to aid in state pollinator conservation efforts.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Build website with training and education resources | 2022-04-30 |
| Update old material and develop new resources, as needed | 2024-06-30 |
| Provide technical support for portal users, as needed | 2024-06-30 |
| Invite teachers and their students across the state to enroll in the portal | 2024-06-30 |

## **Project Partners and Collaborators**

|  |  |  |  |
| --- | --- | --- | --- |
| **Name** | **Organization** | **Role** | **Receiving Funds** |
| John Benning | University of Minnesota, Twin Cities. | Post-doctoral researcher. Co-founder of City Backyard Science. | No |
| Amanda Gorton | University of Minnesota, Twin Cities | Post-doctoral researcher. Co-founder of City Backyard Science. | Yes |

## **Long-Term Implementation and Funding**

**Describe how the results will be implemented and how any ongoing effort will be funded. If not already addressed as part of the project, how will findings, results, and products developed be implemented after project completion? If additional work is needed, how will this be funded?**We will share results with the households, teachers, and communities involved in the project through a bi-annual workshop at the North Mississippi Regional Park. We anticipate publishing our learning assessment results in education journals and as white papers. Project outcomes will provide the basis for sustainable funding through sources like the UMN Institute on the Environment and MN DNR. Moving forward, we envision hundreds of Backyard Science beds across Minnesota. We will provide the plans for building and planting beds, and all science lessons and activities, for free online, so that any Minnesotan can start their own Backyard Science bed.

## **Project Manager and Organization Qualifications**

**Project Manager Name:** Christina Locke

**Job Title:** Senior Scientist

**Provide description of the project manager’s qualifications to manage the proposed project.**Christina Locke is a Senior Scientist in the Keeler Lab at the University of Minnesota, Twin Cities. She has applied her expertise in statistical modeling, GIS, evaluation, and science communication to a number of conservation issues over her professional career. She has experience coordinating large, statewide projects and leading collaborations among agencies, universities, and diverse stakeholder groups. She also has extensive experience mentoring students and early career researchers, and leading groups of researchers in field and lab work.
Before her current position, Christina was a Research Scientist at the Wisconsin Department of Natural Resources where she coordinated the Snapshot Wisconsin citizen science project. She also led a collaboration between the Wisconsin Department of Agriculture and the University of Wisconsin to produce the Wisconsin Pollinator Protection Plan. Her scientific interests include participatory research, spatial analysis, and evaluation, and she particularly enjoys working at the intersection of science and policy. Christina completed a Bachelor's degree in Biology at the University of Wisconsin, Eau Claire, and a PhD focused on land use change and policy from the University of Wisconsin, Madison.

**Organization:** U of MN - Twin Cities

**Organization Description:**The Keeler Lab is a research group at the University of Minnesota’s Humphrey School of Public Affairs and part of the Center for Science, Technology, and Environmental Policy. The Lab uses interdisciplinary approaches, drawing from economics, conservation science, and geospatial analyses to address challenges related to natural resource management and policy. Priority is given to research conducted in partnership with state and federal agencies, environmental and community-based organizations, and other stakeholders seeking solutions to complex environmental management and policy challenges.

## **Budget Summary**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Category / Name** | **Subcategory or Type** | **Description** | **Purpose** | **Gen. Ineli gible** | **% Bene fits** | **# FTE** | **Class ified Staff?** | **$ Amount** |
| **Personnel** |  |  |  |  |  |  |  |  |
| Post-doctoral Researcher |  | Manage project team and logistics |  |  | 25.4% | 3 |  | $189,853 |
| Senior Scientist |  | Principal investigator |  |  | 36.5% | 0.6 |  | $59,654 |
| Summer internships for four high school students @ 50% time per summer for two summers |  | Assist with logistics and community support during growing season |  |  | 8% | 4 |  | $27,226 |
| Graduate Student Researcher-Academic Year |  | Develop and analyze learning assessment tool |  |  | 111.25% | 0.93 |  | $95,639 |
| Graduate Student Researcher-summer session |  | Develop and analyze learning assessment tool |  |  | 19.9% | 0.24 |  | $14,271 |
| Graduate Student Researcher-Academic year |  | Develop curriculum for participants |  |  | 111.25% | 0.74 |  | $76,186 |
| Graduate Student Researcher-summer session |  | Develop curriculum for participants |  |  | 19.9% | 0.12 |  | $7,135 |
|  |  |  |  |  |  |  | **Sub Total** | **$469,964** |
| **Contracts and Services** |  |  |  |  |  |  |  |  |
| TBD | Professional or Technical Service Contract | Carpentry work to build 50 raised garden beds. |  |  |  | - |  | $2,500 |
| TBD | Professional or Technical Service Contract | Develop website and online portal for use by project participants. |  |  |  | - |  | $7,000 |
| TBD | Professional or Technical Service Contract | Advising on study design, analysis, report writing, and other scientific and technical aspects of the project. |  |  |  | - |  | $10,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$19,500** |
| **Equipment, Tools, and Supplies** |  |  |  |  |  |  |  |  |
|  | Tools and Supplies | soil, lumber, plants, seeds, fasteners, glue, weed suppresion paper, and rebar | Supplies for constructing and planting 50 raised garden beds |  |  |  |  | $5,200 |
|  |  |  |  |  |  |  | **Sub Total** | **$5,200** |
| **Capital Expenditures** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Acquisitions and Stewardship** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Travel In Minnesota** |  |  |  |  |  |  |  |  |
|  | Miles/ Meals/ Lodging | Mileage for in-state travel | Travel for project team to visit participant garden beds |  |  |  |  | $1,718 |
|  |  |  |  |  |  |  | **Sub Total** | **$1,718** |
| **Travel Outside Minnesota** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Printing and Publication** |  |  |  |  |  |  |  |  |
|  | Publication | Web hosting fees | Cost of hosting a web domain for 3 years |  |  |  |  | $118 |
|  | Printing | Design software costs and printing costs | Design and print educational materials for participants |  |  |  |  | $500 |
|  |  |  |  |  |  |  | **Sub Total** | **$618** |
| **Other Expenses** |  |  |  |  |  |  |  |  |
|  |  | Venue rental | Cost of renting a venue for the four in-person workshops with project participants |  |  |  |  | $3,000 |
|  |  | Food and beverages | To provide refreshments at the four in-person workshops for project participants. |  |  |  |  | $2,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$5,000** |
|  |  |  |  |  |  |  | **Grand Total** | **$502,000** |

### **Classified Staff or Generally Ineligible Expenses**

|  |  |  |  |
| --- | --- | --- | --- |
| **Category/Name** | **Subcategory or Type** | **Description** | **Justification Ineligible Expense or Classified Staff Request** |

### **Non ENRTF Funds**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Category** | **Specific Source** | **Use** | **Status** | **Amount** |
| **State** |  |  |  |  |
|  |  |  | **State Sub Total** | **-** |
| **Non-State** |  |  |  |  |
|  |  |  | **Non State Sub Total** | **-** |
|  |  |  | **Funds Total** | **-** |

## **Attachments**

### **Required Attachments**

#### **Visual Component**

File: [3c3fe950-6e8.pdf](https://lccmrprojectmgmt.leg.mn/media/map/3c3fe950-6e8.pdf)

#### **Alternate Text for Visual Component**

This visual shows the goals of MN Backyard Science, provides an outline of the project, and includes photos from the pilot phase of the project completed in 2019.

### **Optional Attachments**

#### **Support Letter or Other**

|  |  |
| --- | --- |
| **Title** | **File** |
| Audited Financial Report 2019 | [87931362-beb.pdf](https://lccmrprojectmgmt.leg.mn/media/attachments/87931362-beb.pdf) |
| Institutional Letter of Endorsement | [05a7c300-4e7.doc](https://lccmrprojectmgmt.leg.mn/media/attachments/05a7c300-4e7.doc) |

## **Administrative Use**

**Does your project include restoration or acquisition of land rights?**
 No

**Does your project have patent, royalties, or revenue potential?**
 No

**Does your project include research?**
 Yes

**Does the organization have a fiscal agent for this project?**
 Yes, Sponsored Projects Administration