

**Environment and Natural Resources Trust Fund**

# 2021 Request for Proposal

## **General Information**

**Proposal ID:** 2021-321

**Proposal Title:** Microbiome In Raptors: A New Tool For Conservation

## **Project Manager Information**

**Name:** Julia Ponder

**Organization:** U of MN - Raptor Center

**Office Telephone:** (612) 624-3431

**Email:** ponde003@umn.edu

## **Project Basic Information**

**Project Summary:** We will evaluate the impact of microbial interventions during captivity on the raptor gut microbiome, both in terms of treatment efficacy during rehabilitation and subsequent environmental dissemination.

**Funds Requested:** $129,000

**Proposed Project Completion:** 2023-06-30

**LCCMR Funding Category:** Small Projects (H) **Secondary Category:** Foundational Natural Resource Data and Information (A)

## **Project Location**

**What is the best scale for describing where your work will take place?** Statewide

**What is the best scale to describe the area impacted by your work?** Statewide

**When will the work impact occur?** During the Project and In the Future

## **Narrative**

**Describe the opportunity or problem your proposal seeks to address. Include any relevant background information.**

Antimicrobials and probiotics are both commonly-used therapies in raptor rehabilitation. However, these treatments can alter raptor microbial communities (i.e. microbiomes), which in turn may have unintended consequences for raptor health, as well as wider implications for natural ecosystems. Specifically, exposure to antimicrobials and the treatment of raptors with probiotics formulated for different species may cause long-term harmful perturbations to the gut microbiome, particularly in at-risk individuals. Further, antimicrobials may create selection pressure for antimicrobial resistant bacteria, which could then be introduced into the environment upon reintroduction of animals into their natural habitat. Although antimicrobial resistance (AMR) is one of the greatest public health challenges of the 21st century and wild birds, including raptors, are considered one of the primary mechanisms by which AMR is disseminated in the environment, the impact of AMR on ecosystem health is still largely understudied. As such, it is crucial to understand whether microbial interventions in captivity lead to the release of animals with impaired gut microbiomes that make them less fit for survival as well as create mechanisms for AMR dissemination.

**What is your proposed solution to the problem or opportunity discussed above? i.e. What are you seeking funding to do? You will be asked to expand on this in Activities and Milestones.**

Our goal is to understand the impact raptor rehabilitation (treatment and captivity) has on the raptor gut microbiome and on the emergence and spread of AMR in the natural environment. With this information, we will be able to understand whether we are releasing raptors into the wild with impaired and/or altered microbiomes that make them less fit for survival and ultimately use this information to make improvements to raptor treatment and husbandry. In order to achieve this goal, we are seeking funding to characterize and quantify the gut microbiome and antimicrobial resistance in raptors. Specifically, we will be comparing the gut microbiome of healthy raptors captured at Hawk Ridge Bird Observatory (HRBO) in Duluth MN, during fall migration with injured raptors of the same species admitted to The Raptor Center (TRC) during the same timeframe. We will assess the health of sampled raptors using standard biometrics to link health to gut microbiome outcomes. In addition, we will longitudinally sample raptors admitted at TRC to evaluate the potential emergence and development of antimicrobial resistance before being released back into the wild.

**What are the specific project outcomes as they relate to the public purpose of protection, conservation, preservation, and enhancement of the state’s natural resources?**

We will have an improved understanding of the short- and long-term impacts of microbial interventions during captivity on the raptor gut microbiome and an estimate of AMR risk, both in terms of treatment efficacy during rehabilitation and subsequent environmental dissemination. This project will also advance raptor welfare in rehabilitation settings by providing clinicians with actionable recommendations for treatments and husbandry during rehabilitation and better prognoses for survival after release. As we become more knowledgeable about healthy and altered microbiomes in wildlife species, we will be able to include the microbiome among the important tools for wildlife management and conservation plans.

## **Activities and Milestones**

### **Activity 1: Microbiome analysis and link to raptor health**

**Activity Budget:** $65,453

**Activity Description:**We will collect cloacal samples from raptors at both HRBO and TRC during the fall migration of 2021. At HRBO, raptors will be trapped and sampled with the collaboration of HRBO researchers. The same collection procedures will be used to collect samples from raptors at TRC upon admission prior to any clinical treatment, and at several time points subsequently to evaluate changes in the microbiome over time. We will then extract bacterial DNA from all cloacal swabs and use next generation sequencing technology in combination with bioinformatic analyses to characterize raptor gut microbial communities. To assess the general health of each bird, we will collect measurements of weight, body condition score, and basic hematological parameters. We will take additional morphometric parameters to determine age and sex. We will analyze these data together with the microbiome results to identify associations between raptor health and characteristics of the raptor microbiome.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Raptor sample collection at HRBO (Duluth, MN) for microbiome analysis | 2021-11-30 |
| Raptor sample collection at TRC for microbiome analysis | 2021-12-31 |
| DNA extraction and sequencing | 2022-06-30 |
| Bioinformatics and data analyses | 2022-10-31 |
| Publication and presentation of results at a conference | 2023-05-31 |

### **Activity 2: Evaluation of the emergence of antimicrobial resistance in raptors**

**Activity Budget:** $63,547

**Activity Description:**We will conduct a longitudinal study to evaluate the development of AMR in raptors admitted to TRC. We will include raptors that have a fair prognosis of survival upon admission (to allow for sampling over time) and fall into two groups: raptors that do not receive antibiotic treatment (control group) and raptors that receive at least seven days of continued antibiotic treatment. We will collect two cloacal swabs from all enrolled birds at three time points: 1) at admission prior to any treatment, 2) after treatment (if applicable) and before the bird is moved to a recovery flight enclosure, and 3) before release. We will record information on antimicrobial interventions as well as information about husbandry practices for each bird. We will then utilize the cloacal swabs to conduct antimicrobial susceptibility testing using standard laboratory disk diffusion techniques to characterize resistant bacteria, and we will use a microfluidic qPCR (MF-qPCR) to quantify antibiotic resistance gene differences over time and between groups.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Raptor sample collection at TRC for antimicrobial resistance analyses | 2021-12-31 |
| Laboratory analysis of antibiotic resistant bacteria | 2022-09-30 |
| Laboratory analyses to quantify antibiotic resistance genes (MF-qPCR) | 2023-01-31 |
| Data analyses | 2023-04-30 |
| Publication and presentation of results at a conference | 2023-06-30 |

## **Project Partners and Collaborators**

|  |  |  |  |
| --- | --- | --- | --- |
| **Name** | **Organization** | **Role** | **Receiving Funds** |
| Matthew Etterson | Hawk Ridge Bird Observatory | Collaborator - will provide access to samples of wild-trapped birds during banding season and contribute to data analysis. | No |

## **Long-Term Implementation and Funding**

**Describe how the results will be implemented and how any ongoing effort will be funded. If not already addressed as part of the project, how will findings, results, and products developed be implemented after project completion? If additional work is needed, how will this be funded?**Understanding the links between raptor health and gut microbiome changes will be used as a new tool to tailor treatments of raptors undergoing rehabilitation, which will ultimately contribute to raptor conservation efforts. Results will also provide the first steps toward understanding how microbiome alterations may affect raptor fitness in the wild, as well as how they may contribute to the widespread dissemination of antimicrobial resistance in natural environments. Minnesota will be the pioneer on this front, and results can be later extrapolated to other rehabilitation facilities and ecosystems across the country. Future funding options to expand the work include Morris Animal Foundation, Association of Avian Veterinarians, and National Science Foundation.

## **Other ENRTF Appropriations Awarded in the Last Six Years**

|  |  |  |
| --- | --- | --- |
| **Name** | **Appropriation** | **Amount Awarded** |
| Spruce Grouse as Indicators for Boreal Forest Connectivity | M.L. 2019, First Special Session, Chp. 4, Art. 2, Sec. 2, Subd. 03e | $350,000 |
| Expanding Raptor Center Online Education | M.L. 2017, Chp. 96, Sec. 2, Subd. 05d | $270,000 |
| Game and Nongame Bird Pesticide Exposure | M.L. 2016, Chp. 186, Sec. 2, Subd. 03m | $349,000 |
| Raptor Lab Integrating Online and Outdoor Learning Environments | M.L. 2014, Chp. 226, Sec. 2, Subd. 09h | $186,000 |

## **Project Manager and Organization Qualifications**

**Project Manager Name:** Julia Ponder

**Job Title:** Associate Professor - College of Vet Medicine; Executive Director - The Raptor Center

**Provide description of the project manager’s qualifications to manage the proposed project.**Dr. Ponder is the Executive Director for The Raptor Center and College of Veterinary Medicine faculty member. Dr. Ponder is a veterinary expert in avian health working in a clinical and research environment devoted to birds. She has extensive project management experience, as well as international experience working with non-profits and governmental agencies. She has managed projects varying from $10,000 to $3.7 million, addressing issues as diverse as wildlife health surveillance, community partnerships and international field research.

**Organization:** U of MN - Raptor Center

**Organization Description:**The Raptor Center (TRC) is a University research and outreach center focused on health issues found at the intersection of raptors and humans. TRC provides medical care of over 700 injured and ill raptors each year, trains veterinarians and veterinary students from around the world in conservation medicine and has extensive experience in outreach and environmental education, averaging over 1,000 programs reaching more than 200,000 people throughout Minnesota, Wisconsin, and Iowa annually. For over 30 years, staff at TRC has studied health issues in raptors. In addition, the faculty of The Raptor Center have appointments in the College of Veterinary Medicine, University of Minnesota, a research university.  
  
The University of Minnesota is a highly ranked public research university with a mission that encompasses research and discovery, teaching and learning, and outreach and public service. A land-grant university, it supports research and discovery benefiting the conservation and management of Minnesota’s natural resources. It has well-established systems and processes for management of research awards and financial oversight of grants.

## **Budget Summary**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Category / Name** | **Subcategory or Type** | **Description** | **Purpose** | **Gen. Ineli gible** | **% Bene fits** | **# FTE** | **Class ified Staff?** | **$ Amount** |
| **Personnel** |  |  |  |  |  |  |  |  |
| Project manager |  | Project oversight, coordination and reporting |  |  | 36.5% | 0.1 |  | $21,210 |
| Post Doctoral Associate |  | Survey, sampling, genetic analysis, manuscript writing |  |  | 25.4% | 0.6 |  | $38,651 |
| Researcher |  | Sampling, performs bioinformatics and microbiome analysis; oversees susceptibility testing; manuscript writing |  |  | 36.5% | 0.2 |  | $25,707 |
| Veterinary intern |  | Sample collection, preparation, handling and curation at The Raptor Center |  |  | 22.45% | 0.2 |  | $3,429 |
| Laboratory technician |  | DNA extractions, bacterial culturing, susceptibility testing and sample preparation for genetic analysis |  |  | 31.8% | 0.3 |  | $15,324 |
|  |  |  |  |  |  |  | **Sub Total** | **$104,321** |
| **Contracts and Services** |  |  |  |  |  |  |  |  |
| University of Minnesota Genomics Center | Professional or Technical Service Contract | Genetic sequencing of samples |  |  |  | 0.05 |  | $6,968 |
|  |  |  |  |  |  |  | **Sub Total** | **$6,968** |
| **Equipment, Tools, and Supplies** |  |  |  |  |  |  |  |  |
|  | Tools and Supplies | Laboratory supplies - consumables | Sample collection supplies, reagents, culture supplies and laboratory consumables including solvents, standards, vials and columns |  |  |  |  | $7,925 |
|  |  |  |  |  |  |  | **Sub Total** | **$7,925** |
| **Capital Expenditures** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Acquisitions and Stewardship** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Travel In Minnesota** |  |  |  |  |  |  |  |  |
|  | Miles/ Meals/ Lodging | Mileage | Trips to Hawk Ridge in Duluth MN for sample collection |  |  |  |  | $1,574 |
|  |  |  |  |  |  |  | **Sub Total** | **$1,574** |
| **Travel Outside Minnesota** |  |  |  |  |  |  |  |  |
|  | Conference Registration Miles/ Meals/ Lodging | Travel expenses, per diem and lodging | Travel to scientific meetings to present research results | X |  |  |  | $2,212 |
|  |  |  |  |  |  |  | **Sub Total** | **$2,212** |
| **Printing and Publication** |  |  |  |  |  |  |  |  |
|  | Publication | Open access fees for peer-reviewed journals | Scientific communication of research results |  |  |  |  | $6,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$6,000** |
| **Other Expenses** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
|  |  |  |  |  |  |  | **Grand Total** | **$129,000** |

### **Classified Staff or Generally Ineligible Expenses**

|  |  |  |  |
| --- | --- | --- | --- |
| **Category/Name** | **Subcategory or Type** | **Description** | **Justification Ineligible Expense or Classified Staff Request** |
| **Travel Outside Minnesota** | Conference Registration Miles/Meals/Lodging | Travel expenses, per diem and lodging | Scientific reporting of results at a national conference to be determined based on submission and acceptance of presentation proposal |

### **Non ENRTF Funds**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Category** | **Specific Source** | **Use** | **Status** | **Amount** |
| **State** |  |  |  |  |
|  |  |  | **State Sub Total** | **-** |
| **Non-State** |  |  |  |  |
| In-Kind | Waived facilities and administrative costs | The University of Minnesota is waiving the income normally generated from extramural research grants that contribute Facilities and Administrative (F&A). The current full rate is 55% of direct costs. | Pending | $70,950 |
|  |  |  | **Non State Sub Total** | **$70,950** |
|  |  |  | **Funds Total** | **$70,950** |

## **Attachments**

### **Required Attachments**

#### ***Visual Component***

File: [1c82958c-066.pdf](https://lccmrprojectmgmt.leg.mn/media/map/1c82958c-066.pdf)

#### ***Alternate Text for Visual Component***

The graphic shows the state of Minnesota with marks noting the two locations (University of Minnesota, Hawk Ridge -Duluth) where sampling of birds from around the state will be done, with a picture of an eagle and a flowchart noting how microbiome analysis (Activity 1) and identification of antimicrobial resistance will lead to evidence-based recommendations to improve raptor conservation.

### **Optional Attachments**

#### ***Support Letter or Other***

|  |  |
| --- | --- |
| **Title** | **File** |
| Partnership letter from Hawk Ridge Bird Observatory | [f490d56d-856.pdf](https://lccmrprojectmgmt.leg.mn/media/attachments/f490d56d-856.pdf) |
| Cover letter - University of Minnesota Sponsored Projects | [66f65036-35f.pdf](https://lccmrprojectmgmt.leg.mn/media/attachments/66f65036-35f.pdf) |

## **Administrative Use**

**Does your project include restoration or acquisition of land rights?**   
 No

**Does your project have patent, royalties, or revenue potential?**   
 No

**Does your project include research?**   
 Yes

**Does the organization have a fiscal agent for this project?**   
 Yes, Sponsored Projects Administration