

**Environment and Natural Resources Trust Fund**

# 2021 Request for Proposal

## **General Information**

**Proposal ID:** 2021-380

**Proposal Title:** Accessible Fishing Piers and Shore Fishing Areas

## **Project Manager Information**

**Name:** Nancy Stewart

**Organization:** MN DNR - State Parks and Trails Division

**Office Telephone:** (651) 259-5616

**Email:** nancy.stewart@state.mn.us

## **Project Basic Information**

**Project Summary:** Provide 6-8 accessible fishing piers and 1-2 developed shore fishing sites in locations that have a high potential to serve new angling communities, under-served populations and anglers with disabilities.

**Funds Requested:** $400,000

**Proposed Project Completion:** 2023-12-31

**LCCMR Funding Category:** Land Acquisition for Habitat and Recreation (G)

## **Project Location**

**What is the best scale for describing where your work will take place?** Statewide

**What is the best scale to describe the area impacted by your work?** Statewide

**When will the work impact occur?** In the Future

## **Narrative**

**Describe the opportunity or problem your proposal seeks to address. Include any relevant background information.**

The estimated economic impact of fishing in Minnesota is $2.4 billion and supports more than 35,000 jobs. The Minnesota Department of Natural Resources (DNR) estimates that about 40% of people with Minnesota fishing licenses do not own a boat, this is approximately 480,000 anglers. The requests to the DNR for funding and technical assistance with installing fishing piers and developing shore fishing facilities has been increasing.
Providing angling opportunities and increasing angling participation of youth and families, especially those from under-served populations, is one of the primary goals of the DNR Recruitment, Retention and Reactivation program. Fishing piers and developed shore fishing sites, when available, are often used as classrooms for fishing skills and outdoor education lessons. Three DNR programs will benefit from this project including: MinnAqua; “I Can Fish”; and Fishing in the Neighborhood (FiN). Various groups will also benefit including girl and boy scout organizations, 4-H clubs, local conservation clubs, youth camps, park visitors and surrounding neighborhoods.

**What is your proposed solution to the problem or opportunity discussed above? i.e. What are you seeking funding to do? You will be asked to expand on this in Activities and Milestones.**

Accessible fishing piers and developed shore fishing sites make fishing safe, easy, and fun for all ages, especially children, senior citizens, people with disabilities, veterans, and anyone who does not own a boat. Fishing piers and shore fishing areas help overcome two core barriers of beginning anglers: access (having a safe place to go) and confidence (having fish to catch). Adding new fishing piers and shore fishing sites to lakes and rivers will remove these core barriers, proving additional opportunities and allowing more people to participate.

**What are the specific project outcomes as they relate to the public purpose of protection, conservation, preservation, and enhancement of the state’s natural resources?**

Fishing piers and developed shore fishing areas provide many positive impacts. They provide a safe and convenient place to fish, instead of from fragile, overgrown or rip-rapped shorelines. Fishing pier and shore fishing areas can help in eliminating shoreline erosion caused by repeated angling foot traffic. Around the fishing pier and shore fishing sites, native shoreline and aquatic vegetation can thrive, especially if the projects are paired with shoreline restoration efforts. Fishing piers can also help reduce the carbon footprint by providing an area for people to fish close to home and without a boat.

## **Activities and Milestones**

### **Activity 1: Provide 6-8 accessible fishing piers and 1-2 shore fishing areas in partnership with local government units.**

**Activity Budget:** $350,000

**Activity Description:**Using existing public lands, the MN DNR will work with various local government unit partners to place fishing piers at locations that will: 1) meet ADA requirements; 2) provide an opportunity to catch fish; and 3) serve under-served populations. Through a joint powers agreement, the local government unit partner will assist the MN DNR in maintaining the fishing pier for 20 years and shore fishing area for 30 years. Projects locations are identified as high-priority locations for accessible fishing piers and shore fishing areas. The project list may be modified if a project partner is not able to provide ADA path or maintenance commitments. Changes would be made through a work plan amendment. Some locations are yet to be determined.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Rum River, Sherburne County, City of Princeton, Riverside Park; Shore fishing | 2022-12-31 |
| Fish Lake, St. Louis County, partnership with MN Power, Fishing Pier | 2022-12-31 |
| Sauk River, Stearns County, City of Cold Spring, Fishing Pier | 2022-12-31 |
| Other locations for fishing piers and shore fishing area to be determined | 2023-12-31 |
| Kraemer Lake, Stearns County, Kraemer Lake County Park, Fishing Pier | 2023-12-31 |

### **Activity 2: Personnel costs for technical assistance for project execution and project support**

**Activity Budget:** $50,000

**Activity Description:**Program staff are involved in providing technical expertise, developing and managing partnership agreements, ordering fishing piers and other supplies, installing fishing piers or shore fishing structures. Including fleet costs for vehicles and equipment and the DNR direct and necessary costs associated with this funding.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Technical expertise such as site preparation, delivery, placement and installation. | 2023-12-31 |
| Other costs for project completion, fleet and direct and necessary. | 2023-12-31 |

## **Project Partners and Collaborators**

|  |  |  |  |
| --- | --- | --- | --- |
| **Name** | **Organization** | **Role** | **Receiving Funds** |
| Kraemer Lake Fishing Pier | Stearns County | As the land land owner and site administrator, Stearns County will enter into a partnership agreement for installation and maintenance of the fishing pier with the DNR. Potential monetary and in kind donations for the project are to be determined. | No |
| Rum River Shore Fishing Area | City of Princeton | As the land land owner and site administrator, the City of Princeton will enter into a partnership agreement for installation and maintenance of the fishing pier with the DNR. Potential monetary and in kind donations for the project are to be determined. | No |
| Fish Lake Fishing Pier | Minnesota Power | As the land land owner and site administrator, Minnesota Power will enter into a partnership agreement for installation and maintenance of the fishing pier with the DNR. Potential monetary and in kind donations for the project are to be determined. | No |
| Sauk River Fishing Pier | City of Cold Springs | As the land land owner and site administrator, the City of Cold Springs will enter into a partnership agreement for installation and maintenance of the fishing pier with the DNR. Potential monetary and in kind donations for the project are to be determined. | No |

## **Long-Term Implementation and Funding**

**Describe how the results will be implemented and how any ongoing effort will be funded. If not already addressed as part of the project, how will findings, results, and products developed be implemented after project completion? If additional work is needed, how will this be funded?**Game and Fish funds are used to operate and maintain the DNR’s fishing pier program. The funds pay for staff time, parts, supplies, maintenance and replacement of fishing piers statewide. The program is successful because of the many partnerships with local units of government who provide the day to day maintenance. Fishing piers will be maintained a minimum of 20 years and shore fishing sites 30 years. Two and half years will be needed to complete the fishing pier and shore fishing projects in order to take advantage of the open water season.

## **Other ENRTF Appropriations Awarded in the Last Six Years**

|  |  |  |
| --- | --- | --- |
| **Name** | **Appropriation** | **Amount Awarded** |
| Accessible Fishing Piers | M.L. 2019, First Special Session, Chp. 4, Art. 2, Sec. 2, Subd. 09f | $320,000 |

## **Project Manager and Organization Qualifications**

**Project Manager Name:** Nancy Stewart

**Job Title:** Water Recreation Consultant

**Provide description of the project manager’s qualifications to manage the proposed project.**Nancy Stewart has worked for the State of Minnesota for over 12 years. Her current position is the water recreation consultant in the Parks and Trail Division. She administers the water recreation programs, specifically the operation and maintenance of the state’s public water access, water trail and fishing pier programs. She has extensive experience with multiple funding sources and reports, including the water recreation account, Game and Fish Fund, Federal Sport Fish Restoration Account and Federal Coast Guard account. She is in her first funding cycle with LCCMR having received FY19 funding for accessible fishing piers.

**Organization:** MN DNR - State Parks and Trails Division

**Organization Description:**The mission of the Minnesota Department of Natural Resources (DNR) is to work with Minnesotans to conserve and manage the state's natural resources, to provide outdoor recreation opportunities, and to provide for commercial uses of natural resources in a way that creates a sustainable quality of life. The vision of the Division of Parks and Trails is to create unforgettable park, trail, and water recreation experiences that inspire the public to pass along the love for the outdoors to the next generation. More information on the Minnesota DNR can be found at MNDNR.gov

## **Budget Summary**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Category / Name** | **Subcategory or Type** | **Description** | **Purpose** | **Gen. Ineli gible** | **% Bene fits** | **# FTE** | **Class ified Staff?** | **$ Amount** |
| **Personnel** |  |  |  |  |  |  |  |  |
| Technicians and Laborers |  | Site preparation and installation of piers |  |  | 30% | 0.25 | X | $39,150 |
|  |  |  |  |  |  |  | **Sub Total** | **$39,150** |
| **Contracts and Services** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Equipment, Tools, and Supplies** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Capital Expenditures** |  |  |  |  |  |  |  |  |
|  |  | Fishing piers (6-8) | Floating fishing piers of various lengths for installation at project location to provide safe access and increase angling opportunities.. |  |  |  |  | $240,000 |
|  |  | Shore fishing area construction and supplies (1-2) | Accessible structure on shore, usually along rivers, to provide safe access and increase angling opportunities. |  |  |  |  | $110,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$350,000** |
| **Acquisitions and Stewardship** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Travel In Minnesota** |  |  |  |  |  |  |  |  |
|  | Miles/ Meals/ Lodging | Miles - Fleet charges for vehicle and heavy equipment | For the site preparation and installation |  |  |  |  | $1,011 |
|  |  |  |  |  |  |  | **Sub Total** | **$1,011** |
| **Travel Outside Minnesota** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Printing and Publication** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Other Expenses** |  |  |  |  |  |  |  |  |
|  |  | DNR Direct and Necessary | Support (people, safety, financial, communications, IT, planning) |  |  |  |  | $9,839 |
|  |  |  |  |  |  |  | **Sub Total** | **$9,839** |
|  |  |  |  |  |  |  | **Grand Total** | **$400,000** |

### **Classified Staff or Generally Ineligible Expenses**

|  |  |  |  |
| --- | --- | --- | --- |
| **Category/Name** | **Subcategory or Type** | **Description** | **Justification Ineligible Expense or Classified Staff Request** |
| **Personnel** - Technicians and Laborers |  | Site preparation and installation of piers | **Classified :** Existing staff with experience will be used for the project site preparations and installations, many who can operate heavy equipment. There will be other work not performed by these staff in order to complete these projects. The positions often have a variety of funding sources from year to year. |

### **Non ENRTF Funds**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Category** | **Specific Source** | **Use** | **Status** | **Amount** |
| **State** |  |  |  |  |
|  |  |  | **State Sub Total** | **-** |
| **Non-State** |  |  |  |  |
| In-Kind | Labor and supplies provided by partners as agreed upon in the cooperative agreements. | Site preparation, installation of accessible paths and foundations, installation of fishing piers, | Potential | $30,000 |
| Cash | Donations/partner contributions for the projects | Funds will be used as agreed upon in the cooperative agreement, most likely for the purchase of the fishing pier or construction of the shore fishing area. | Potential | $40,000 |
|  |  |  | **Non State Sub Total** | **$70,000** |
|  |  |  | **Funds Total** | **$70,000** |

## **Attachments**

### **Required Attachments**

#### **Visual Component**

File: [cc5e51b0-130.docx](https://lccmrprojectmgmt.leg.mn/media/map/cc5e51b0-130.docx)

#### **Alternate Text for Visual Component**

Picture of an accessible path and fishing pier located on Rainy Lake, Tilson Bay in St. Louis County.

## **Administrative Use**

**Does your project include restoration or acquisition of land rights?**
 No

**Does your project have patent, royalties, or revenue potential?**
 No

**Does your project include research?**
 No

**Does the organization have a fiscal agent for this project?**
 No