

**Environment and Natural Resources Trust Fund**

# 2021 Request for Proposal

## **General Information**

**Proposal ID:** 2021-433

**Proposal Title:** White Nose Bat Syndrome Biological Control: Phase 3

## **Project Manager Information**

**Name:** Christine Salomon

**Organization:** U of MN - College of Pharmacy

**Office Telephone:** (612) 626-3698

**Email:** csalomon@umn.edu

## **Project Basic Information**

**Project Summary:** Testing of best biocontrol microbes for controlling white nose syndrome (WNS) in bats: Mapping of fungal pathogen, field testing, and assessment of a WNS-free cave with healthy bats

**Funds Requested:** $449,000

**Proposed Project Completion:** 2024-06-30

**LCCMR Funding Category:** Aquatic and Terrestrial Invasive Species (D)

## **Project Location**

**What is the best scale for describing where your work will take place?** Statewide

**What is the best scale to describe the area impacted by your work?** Statewide

**When will the work impact occur?** During the Project and In the Future

## **Narrative**

**Describe the opportunity or problem your proposal seeks to address. Include any relevant background information.**

White nose syndrome (WNS) is a devastating fungal disease of hibernating bats which has killed at least 90% of little brown bats (Myotis lucifugus) at many sites in Minnesota. Our proposal is focused on developing a biocontrol strategy to treat substrates and to monitor the fungal pathogen, Pseudogymnoascus destructans, in Minnesota hibernacula. Our previous research supported by LCCMR and USFW has allowed us to build a library of potential biocontrol microbes (>2000 strains) collected from major hibernacula (Soudan Iron Mine, Mystery Cave, and several sandstone caves). We have screened many of these strains, identified the most potent inhibitors, and are ready to test these strains/extracts on natural substrates and in limited field settings. We have also optimized a sensitive DNA based detection method (qPCR) and used this approach to measure the occurrence and abundance of P. destructans along transects of Mystery Cave and in the Soudan Mine (the two largest hibernacula in Minnesota). This quantification work will be combined with a method to assess viable (live) versus dead cells and spores, which should allow for a more accurate assessment of treatments.

**What is your proposed solution to the problem or opportunity discussed above? i.e. What are you seeking funding to do? You will be asked to expand on this in Activities and Milestones.**

We propose to continue monitoring P. destructans to better understand where the fungus is most abundant and likely to re-infect surviving/returning bats. This approach will be used to monitor treatment experiments, and this data will also be available to park managers to identify specific locations in Soudan Mine and Mystery Cave State Parks to focus treatments, decontamination of equipment, or to help regulate visitors/staff in those areas. Additionally, we recently identified one hibernaculum that surprisingly has a healthy population of tricolor bats (another Minnesota bat species that has been decimated in other nearby locations). An initial, small-scale test of some of the surfaces of this cave were negative for the presence of P. destructans. We propose to determine how this cave has remained free of P. destructans and WNS by studying the physical environment, substrates, and microbial populations. This information may help to develop a treatment strategy for other hibernacula, and to support conservation efforts for surviving bats.

**What are the specific project outcomes as they relate to the public purpose of protection, conservation, preservation, and enhancement of the state’s natural resources?**

Our primary goal is to develop a safe and effective product and treatment strategy to reduce the reservoir of WNS pathogen in hibernacula and ultimately reduce infection rates for our remaining bats (and new pups). Our regular sampling and quantification before and after any test treatments will also provide empirical data to assess management strategies. We will also be studying a hibernacula with healthy bats to provide provide information about a naturally disease suppressive environment which could inform management strategies.

## **Activities and Milestones**

### **Activity 1: Testing of most active microbial biocontrol agents with relevant substrates and field studies**

**Activity Budget:** $172,168

**Activity Description:**We identified >100 microbial strains that inhibit the growth of P. destructans. Among these strains, 10 have demonstrated consistent production of antifungal extracts, and we have purified and identified most of the active compounds. We have also tested these compounds against cultured fibroblast (skin) cells from two species of bats (Northern long eared and Gray bats) to assess their toxicity. The strains that produce the most antifungal but least toxic compounds were prioritized, and these will be applied to natural substrates from the three major hibernacula locations together with P. destructans. We will also test extracts and the active compounds on substrates with established P. destructans. Experimental substrate challenges will be treated with a viability reagent propidium monoazide (PMA) before DNA extraction to differentiate between DNA from live versus dead P. destructans. qPCR with a specific Taqman probe will be used to quantify DNA from live cells. Once these experiments are analyzed, successful trials will be translated into small-scale field experiments in collaboration with the DNR. These experiments will be focused on human-made hibernacula including mines and smaller historic sandstone brewery caves that serve as hibernacula. P. destructans and antagonist growth in these field studies will be assessed by qPCR.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Optimization and testing of top (3-5) biocontrol agents/extracts on natural substrates | 2022-12-31 |
| Field testing of best biocontrol agents, extracts and pure compounds | 2024-06-30 |
| Quantification of P. destructans on substrates in lab and field experiments | 2024-06-30 |

### **Activity 2: Quantification of viable P. destructans in hibernacula: Seasonal and spatial dynamics**

**Activity Budget:** $132,415

**Activity Description:**Bats afflicted with WNS change their hibernation patterns within caves, and will often move towards the entrance of caves. However, little is known about the extent of the environmental reservoirs of viable P. destructans on substrates in these different locations over time. We will map the occurrence and quantity of P. destructans along transects of hibernacula at twice per year from substrate locations (walls, sediments, ceiling) to better understand the spatial and seasonal dynamics of P. destructans growth and potential spread. Samples will be analyzed by treating with PMA (as in activity 1) before isolation of DNA and subsequent qPCR quantification of P. destructans. This information will be especially helpful to cave managers for focusing treatments or interventions. For example, the top of one door at the entrance of Mystery Cave in Forestville was found to have 3000x more P. destructans DNA than areas much deeper in the cave. These “pinch points” for bat entry/exit might be an obvious place for reinfection when bats return in the fall, and could be specifically disinfected. Our regular sampling and quantification before and after any treatments will also provide empirical data to assess management strategies.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| qPCR quantification and viability of samples collected from hibernacula transects, 2x per year, 3 years | 2024-06-30 |

### **Activity 3: Assessment of WNS-free cave**

**Activity Budget:** $144,417

**Activity Description:**We identified a cave (not named here to minimize potential disturbance) with a healthy population of tricolor bats (Perimyotis subflavus) and no signs of WNS (as of 02/2019) with animal numbers consistent with pre-WNS census data. A preliminary analysis of a small number of substrates were all negative, suggesting that P. destructans is not present or not abundant in sampled areas. This is surprising and unexpected due to the widespread occurrence of WNS in all other Minnesota hibernacula. We propose to conduct a more thorough mapping of P. destructans throughout this cave (see activity 2) and from bats over the next three years, and methodically test a number of different possible factors that might be responsible for the absence of WNS. Various substrates (rocks, water, sediment, etc.) will be tested for their ability to host (or inhibit) P. destructans growth, and volatile air samples may be collected and tested. Concurrently, bacterial and fungal samples will be collected and tested for P. destructans inhibition. If the substrate or volatile materials show significant activity, the microbial experiments will be minimized. The results of these experiments should provide information about a naturally disease suppressive environment which will inform management strategies.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Substrate testing against P. destructans | 2022-06-30 |
| Microbial sampling, isolation and testing (depending on results of substrate testing) | 2023-06-30 |
| qPCR quantification of P. destructans on bat and substrate samples throughout cave | 2024-06-30 |

## **Project Partners and Collaborators**

|  |  |  |  |
| --- | --- | --- | --- |
| **Name** | **Organization** | **Role** | **Receiving Funds** |
| Robert Blanchette | University of Minnesota, Department of Plant Pathology | Dr. Blanchette will be responsible for the qPCR analysis of pathogen populations and isolations/characterization of fungi from the WNS-free cave | Yes |

## **Long-Term Implementation and Funding**

**Describe how the results will be implemented and how any ongoing effort will be funded. If not already addressed as part of the project, how will findings, results, and products developed be implemented after project completion? If additional work is needed, how will this be funded?**If we accomplish the goals in this proposal, we expect this to be the last request for the basic research components of this WNS project. Depending on the success of the field trials, we may request additional funds to expand treatments or interventions (such as targeted disinfection) to more hibernacula sites. We plan to continue to request funds from USFW to leverage effort towards WNS treatment (which funded this work through a grant from 2019-2020), and will seek additional funds from the National Science Foundation to expand studies of the natural history and environmental reservoir of P. destructans.

## **Other ENRTF Appropriations Awarded in the Last Six Years**

|  |  |  |
| --- | --- | --- |
| **Name** | **Appropriation** | **Amount Awarded** |
| Biological Control of White Nose Syndrome in Bats - Phase II | M.L. 2016, Chp. 186, Sec. 2, Subd. 06d | $452,000 |

## **Project Manager and Organization Qualifications**

**Project Manager Name:** Christine Salomon

**Job Title:** Associate Professor

**Provide description of the project manager’s qualifications to manage the proposed project.**Dr. Salomon (PI) is an Associate Professor at the Center for Drug Design and a faculty member in the Biotechnology Institute at the University of Minnesota. Dr. Salomon earned her Ph.D. at the Scripps Institution of Oceanography, UCSD, in the area of natural products chemistry from invertebrates and microbes. She continued her training in the Department of Microbiology at the University of Minnesota where she worked on understanding how soil microbes biosynthesize chemical compounds. Dr. Salomon’s current research program is focused on the discovery and utilization of novel microbes that can be used for biological control of agricultural and wildlife pathogens and production of unique compounds for biomedical and biotechnological applications. She has successfully secured both internal (Academic Health Center, Biotechnology Institute) and external (US Department of Agriculture and US Fish and Wildlife) support for her research program. Dr. Salomon is the Principal Investigator on a currently funded ENRTF project "Biological Control of White Nose Syndrome in Bats – Phase II", ML 2016 Chp 186, sec 2.

Dr. Robert Blanchette (Co-PI) is a professor in the Department of Plant Pathology. He has been involved with research and teaching of forest and landscape trees at the University for over 30 years. He currently teaches undergraduate and graduate classes at the University of Minnesota on forest and shade tree diseases. Research is in the area of forest pathology and wood microbiology with investigations underway on the biology and ecology of tree pathogens, tree defense mechanisms and managing tree diseases using integrated control procedures. Dr. Blanchette has served as project leader on several past projects including 2015-084 Preventing a new disease of pines in Minnesota, 2013-19B Finding Disease Resistant Elm Trees in Minnesota and 2016-131-D Winning the Dutch elm disease battle Phase II.

**Organization:** U of MN - College of Pharmacy

**Organization Description:**Dr. Salomon is in the Center for Drug Design at the University of Minnesota and a member of the Biotechnology Institute. These centers play a central role in providing training and coordinating research in biological, chemical and engineering sciences at the University of Minnesota. The University of Minnesota Biotechnology Institute was established to catalyze the development of a biotechnology industry in Minnesota. It also serves as an important resource for industry by providing connections with academic research partners.

The Department of Plant Pathology at the University of Minnesota is one of the oldest plant pathology departments in the country. Since 1907 the Department has had a strong impact on plant health, agricultural development, and ecosystem vitality on a local, national, and international scale. It is involved with solving today's complex plant health problems through cutting-edge research. The department provides sound plant health advice to stakeholders throughout Minnesota and around the globe and is educating the next generation of plant health professionals and change-makers through a modern and broad plant pathology curriculum.

## **Budget Summary**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Category / Name** | **Subcategory or Type** | **Description** | **Purpose** | **Gen. Ineli gible** | **% Bene fits** | **# FTE** | **Class ified Staff?** | **$ Amount** |
| **Personnel** |  |  |  |  |  |  |  |  |
| Principle Investigator |  | Project mananager and chemistry and bioactivity testing lead. |  |  | 36.5% | 0.15 |  | $28,128 |
| Postdoctoral researcher |  | Collecting and testing substrates and volatile samples, fractionation and identification of active components. Microbial isolations and characterizations. Field experiments with test biocontrol strains |  |  | 25.4% | 3 |  | $199,126 |
| Research Associate |  | Sample collection and qPCR analysis of samples for P. destructans quantification in field and laboratory experiments. Fungal isolations and characterizations. |  |  | 36.5% | 0.75 |  | $84,627 |
| Technician |  | biological assay testing, database management for bioactivity, chemistry and microbiology samples, general lab support |  |  | 0% | 1.5 |  | $40,923 |
| undergraduate research assistant |  | media and sample prep, sample management, fungal cultivations, general lab support |  |  | 0% | 0.75 |  | $20,461 |
| Co-Principal Investigator |  | Manager for qPCR analysis of pathogen and fungal isolations |  |  | 0% | 0.15 |  | - |
|  |  |  |  |  |  |  | **Sub Total** | **$373,265** |
| **Contracts and Services** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Equipment, Tools, and Supplies** |  |  |  |  |  |  |  |  |
|  | Tools and Supplies | Microbiology supplies: media, reagents, petri dishes, tubes, gloves, field sampling materials | microbiology field work and assays, activity 1, 3 yrs |  |  |  |  | $8,235 |
|  | Tools and Supplies | Microscopy supplies: microscope use, fixatives, sample prep instrumentation, sample supplies | microscopic characterization of biological control experiments, Activity 1, 3 yrs |  |  |  |  | $4,500 |
|  | Tools and Supplies | Microbiology supplies (media, reagents, petri dishes, tubes, gloves, field sampling materials) | Collection and analysis supplies for quantifying viable P. destructans |  |  |  |  | $8,000 |
|  | Tools and Supplies | Molecular biology/sequencing costs: (DNA isolation kits, PCR supplies, enzymes, reagents, sequencing costs) x 300 samples/year | materials for isolating and sequencing DNA for activity 2, 3 years |  |  |  |  | $12,000 |
|  | Tools and Supplies | Chemical supplies (solvents, chromatography materials, reagents, tubes, glassware, pipettes) | supplies for conducting chemical extractions, fractionation and analysis of substrates and microbial samples for activity 3, 2 years |  |  |  |  | $18,000 |
|  | Tools and Supplies | Supplies for biological assays (pipettes, pipette tips, epi tubes, culture tubes, petri dishes, media, 96 well plates, reagents, gloves), estimated 300 samples per year | Supplies for conducting biological antifungal assays with extracts/compounds/substrates obtained for activity 3, 3 years |  |  |  |  | $14,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$64,735** |
| **Capital Expenditures** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Acquisitions and Stewardship** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Travel In Minnesota** |  |  |  |  |  |  |  |  |
|  | Miles/ Meals/ Lodging | In-state round trip travel : room/board for 2-3 researchers for overnight trips, mileage, est. 5-6 trips/yr (1-3 days each trip) for 3 yrs | For collection of samples from caves/mines throughout Minnesota, all activities x 3 yrs |  |  |  |  | $6,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$6,000** |
| **Travel Outside Minnesota** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Printing and Publication** |  |  |  |  |  |  |  |  |
|  | Publication | ~2 total, $1000 per publication-page/color fee charges and/or open access charges for publishing scientific manuscripts | Publication of scientific data and results obtained during this project |  |  |  |  | $2,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$2,000** |
| **Other Expenses** |  |  |  |  |  |  |  |  |
|  |  | Repair of equipment and instrumentation (e.g. vacuum pumps, water baths, incubators, shakers, etc.) and calibration of instruments (pipettes, balances) estimated at $1000 per year for 3 years | Funds for inevitable breakage, repair of glassware and instrumentation and calibration of instrumentation |  |  |  |  | $3,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$3,000** |
|  |  |  |  |  |  |  | **Grand Total** | **$449,000** |

### **Classified Staff or Generally Ineligible Expenses**

|  |  |  |  |
| --- | --- | --- | --- |
| **Category/Name** | **Subcategory or Type** | **Description** | **Justification Ineligible Expense or Classified Staff Request** |

### **Non ENRTF Funds**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Category** | **Specific Source** | **Use** | **Status** | **Amount** |
| **State** |  |  |  |  |
|  |  |  | **State Sub Total** | **-** |
| **Non-State** |  |  |  |  |
|  |  |  | **Non State Sub Total** | **-** |
|  |  |  | **Funds Total** | **-** |

## **Attachments**

### **Required Attachments**

#### ***Visual Component***

File: [89f6590e-63e.pdf](https://lccmrprojectmgmt.leg.mn/media/map/89f6590e-63e.pdf)

#### ***Alternate Text for Visual Component***

A map of Minnesota showing the locations of the 3 major bat hibernacula areas, with a typical

## **Administrative Use**

**Does your project include restoration or acquisition of land rights?**
 No

**Does your project have patent, royalties, or revenue potential?**
 Yes,

 • Patent, Copyright, or Royalty Potential

 • Potential revenue generated or net income from the sale of products or assets developed or acquired with ENRTF funding

**Does your project include research?**
 Yes

**Does the organization have a fiscal agent for this project?**
 Yes, Sponsored Projects Administration