

**Environment and Natural Resources Trust Fund**

# 2022 Request for Proposal

## **General Information**

**Proposal ID:** 2022-149

**Proposal Title:** Offal Wildlife Watching: How Do Hunters Provision Scavengers?

## **Project Manager Information**

**Name:** Joseph Bump

**Organization:** U of MN - College of Food, Agricultural and Natural Resource Sciences

**Office Telephone:** (612) 624-2255

**Email:** bump@umn.edu

## **Project Basic Information**

**Project Summary:** This is a citizen-science project driven by hunters. We'll recruit hunters statewide and provide remote cameras to deploy at field-dressed deer gut piles to study scavengers, hunter provisioning, and CWD.

**Funds Requested:** $531,000

**Proposed Project Completion:** June 30 2024

**LCCMR Funding Category:** Foundational Natural Resource Data and Information (A)

## **Project Location**

**What is the best scale for describing where your work will take place?** Statewide

**What is the best scale to describe the area impacted by your work?** Statewide

**When will the work impact occur?** During the Project and In the Future

## **Narrative**

**Describe the opportunity or problem your proposal seeks to address. Include any relevant background information.**

There's a tremendous opportunity for Minnesota deer hunters to help collect data about scavenger species that consume what successful hunters leave behind in the field. Every year hunters harvest ~200,000 deer across the state and almost all hunters field-dress their deer immediately, i.e. they remove the internal organs, or offal, from the deer to cool the carcass down quickly to avoid spoiling. Virtually all offal is left in the field, resulting in more than 4-million pounds of nutritious resources that are consumed by numerous wildlife species.   
  
Yet, there are no Minnesota data on scavenger dynamics at hunter-provided deer offal. How many species use deer offal? Which species use offal the most? How long does offal last on the landscape? Are there risks to specific scavenger species, such as bald eagles, that involve consumption of contaminants? Are there potential disease exposure and transmission issues, such as chronic wasting disease? Do answers to these questions vary across biomes from the boreal northeast to the farms and prairies of the southwest?   
  
Answers to these questions will inform wildlife monitoring and management statewide. And our solution to the problem will enlist those perfectly suited to help solve the problem - hunters.

**What is your proposed solution to the problem or opportunity discussed above? i.e. What are you seeking funding to do? You will be asked to expand on this in Activities and Milestones.**

We seek funding to develop a statewide citizen science program that will address this knowledge gap by recruiting and providing remote cameras to hunters to deploy at their field-dressed deer offal piles. There is no other way to efficiently collect sufficient images statewide other than working with hunters. Images will then be gathered from hunters, archived, and analyzed to address management questions.  
  
We have already piloted this program over three hunting seasons, during which we recruited ~280 hunters that were eager to help. Images were gathered from ~140 hunters that harvested deer, thereby demonstrating a successful approach. Yet, hunter participation is lower than what is needed and our spatial coverage across the state is inadequate.  
   
Minnesota has distinct biomes and variable human densities that range from wilderness to a major metropolitan area. Deer hunting occurs in each of these areas and as a result, hunter provided offal is made available to scavengers across the state. We will develop a program to manage volunteer recruitment, training, data collection and storage, assessment of key questions, and outreach.   
  
Partners: Minnesota Master Naturalist Program, Minnesota 4-H, Minnesota Deer Hunters Association, Backcountry Hunters & Anglers, Bluffland Whitetails Association, Minnesota Center for Prion Research and Outreach.

**What are the specific project outcomes as they relate to the public purpose of protection, conservation, preservation, and enhancement of the state’s natural resources?**

This project has two main outcomes: 1) producing data that fill a knowledge gap needed for better wildlife protection and preservation (including potential exposure to contaminants/disease), and 2) creating a novel and meaningful program for hunter participation in citizen science and enhancement of natural resources. This project will result in a comprehensive understanding of scavenger at hunter provided offal. With the significant added increase in cameras and participants, we will be able to generate statewide data to capture variation in scavenger responses. With this information, we can better understand the benefits and potential risks of offal resources for scavengers.

## **Activities and Milestones**

### **Activity 1: Recruit statewide and train volunteer hunters to participate in the Offal Wildlife Watching project.**

**Activity Budget:** $130,000

**Activity Description:**The objective of this activity is to attract, inform, and enlist the help of volunteer hunters to participate in the Offal Wildlife Watching project statewide. To accomplish this objective we will facilitate volunteer recruitment and training through well designed events and resources. This will involve tasks such as traveling statewide to diverse groups including the Minnesota Master Naturalists Program, Minnesota Deer Hunters Association, Minnesota Backcountry Hunters and Anglers, Bluffland Whitetails Association, 4-H, Tribal Nations, and The Wildlife Society. We will also expand our social media presence and design informative media and handouts related to project recruitment. As an outcome, we have a goal of doubling our annual participation to ~400 and increasing our spatial coverage to better represent all of Minnesota’s habitats.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Master Naturalist Advanced Training | August 31 2022 |
| Recruit and train 250 volunteers for 2022 hunting season | November 30 2022 |
| Master Naturalist Advanced Training | August 31 2023 |
| Recruit and train 250 volunteers for 2023 hunting season | November 30 2023 |

### **Activity 2: Image data collection via hunter deployed remote camera traps at deer offal piles, followed by data entry, archive, and analysis.**

**Activity Budget:** $350,000

**Activity Description:**The first objective of this activity is to work with hunter volunteers to collect images via deployed remote camera traps at deer offal piles. Once images have been recorded, our next objective is to gather images from hunters, back them up and archive copies, enter individual hunter site data, and analyze images to answer key management questions such as: How many species use deer offal? Which species use offal the most? How long does offal last on the landscape?   
  
To accomplish these objectives, we will have remote camera kits to share with hunters that need them. Images will be collected from hunters remotely online, via mail, and in person. Data will be backed up and archived in two ways: with external hard drives and high density storage at the University of Minnesota’s Supercomputing Institute. A postdoctoral researcher with extensive experience with the project will be 100% dedicated to data analysis.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Order, program, and prepare 500 remote camera trapping kits | September 30 2022 |
| Image data collecting from hunters 2022 | February 28 2023 |
| Image backup and archive 2023 | March 31 2023 |
| Image data collecting from hunters 2023 | February 28 2024 |
| Image backup and archive 2023 | March 31 2024 |
| Data analysis and summary (ongoing) | June 30 2024 |

### **Activity 3: Dissemination of results and public outreach via social media, presentations, publications, and popular articles.**

**Activity Budget:** $51,000

**Activity Description:**The objective of this activity is to share project results with hunter volunteers and disseminate information to the public. To accomplish this objective we will prepare popular and scientific presentations that will be given to participating groups and hunters. We will prepare popular articles such as those featured in the Minnesota Conservation Volunteer and manuscripts for publication in peer-reviewed journals. We will create content for social media outlets and training for Minnesota Master Naturalist and other groups engaged with Minnesota natural resources stewardship.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Present at the 2022 Minnesota Chapter of The Wildlife Society meeting | February 28 2023 |
| Present at the 2023 Minnesota Chapter of The Wildlife Society meeting | February 28 2024 |
| Present at 2023 Minnesota Master Naturalist Gathering Partners conference | May 31 2024 |
| Present at 2024 Minnesota Master Naturalist Gathering Partners conference | June 30 2024 |
| Present for the Minnesota Deer Hunters Association | June 30 2024 |

## **Project Partners and Collaborators**

|  |  |  |  |
| --- | --- | --- | --- |
| **Name** | **Organization** | **Role** | **Receiving Funds** |
| Nathan Meyer | University of Minnesota | Extension Program Leader focused on forestry, fisheries and wildlife programming and outreach who will supervise hunter recruitment and training efforts. | Yes |
| Amy Rager | University of Minnesota | Extension Program Leader focused on forestry, fisheries and wildlife programming, and outreach. Ms. Rager will assist in hunter recruitment and training efforts, and outreach efforts especially among members of the Minnesota Master Naturalist program. | Yes |
| Craig Engwall | Minnesota Deer Hunters Association (MDHA) | Lead liaison with MDHA. Mr. Engwall is the Executive Director of the Minnesota Deer Hunters Association (MDHA) | No |
| Nicole Pokorney | University of Minnesota | Lead liaison with Minnesota 4-H. Ms. Pokorney is an Extension educator with Center for Youth Development. | No |
| Matthew Lee | Minnesota chapter of Backcountry Hunters and Anglers (BHA) | Lead liaison with the Minnesota chapter of BHA. Mr. Lee is the BHA Minnesota chapter chair. | No |
| Taylor Bestor | Bluffland Whitetails Association | Lead liaison with Bluffland Whitetails Association. Mr. Bestor is the President of Bluffland Whitetails association. | No |
| Dr. Tiffany Wolf and Dr. Peter Larsen | Minnesota Center for Prion Research and Outreach | To explore ways in which hunter collaboration may be leveraged for Chronic Wasting Disease research (CWD) and to support additional opportunities it may offer to advance CWD research. | No |

## **Long-Term Implementation and Funding**

**Describe how the results will be implemented and how any ongoing effort will be funded. If not already addressed as part of the project, how will findings, results, and products developed be implemented after project completion? If additional work is needed, how will this be funded?**Our goal is to develop this program into a long-term University of Minnesota Extension program that not only continues to engage hunters in the Offal Wildlife Watching project, but expands the program to bear hunter bait piles and hunter surveys as well. A point of expansion would be to assess why some hunters are currently choosing to participate while others do not, which may better allow us to engage more hunters. Such an ongoing effort would likely involve a phase two funding proposal submitted ENRTF and University of Minnesota support. We'll collaborate with the Minnesota Center for Prion Research long-term.

## **Other ENRTF Appropriations Awarded in the Last Six Years**

|  |  |  |
| --- | --- | --- |
| **Name** | **Appropriation** | **Amount Awarded** |
| Mapping Aquatic Habitats for Moose | M.L. 2019, First Special Session, Chp. 4, Art. 2, Sec. 2, Subd. 03l | $199,000 |

## **Project Manager and Organization Qualifications**

**Project Manager Name:** Joseph Bump

**Job Title:** Associate Professor, Gullion Chair; Director of Graduate Studies, Conservation Science Program

**Provide description of the project manager’s qualifications to manage the proposed project.**PROJECT MANAGER QUALIFICATIONS:   
Dr. Joseph K. Bump is an Associate Professor and the Gordon W. Gullion Chair in Forest Wildlife Research and Education in the Department of Fisheries, Wildlife, and Conservation Biology at the University of Minnesota. Dr. Bump’s expertise is in wildlife ecology, management, and conservation, with a focus on large mammals. He has worked on carcass ecology and scavenger related research and management for the past 17 years. Most recently his doctoral student initiated and piloted the “Offal Wildlife Watching” project, which involves Minnesota deer hunter participation in collecting data on scavenger use of gut piles from field-dressed deer. This work is directly relevant to understanding wildlife community exposure to possible disease and environmental contaminant nodes.   
  
Professional preparation  
Michigan Technological University, Ph.D., Forest Science - wildlife ecology focus, Rolf O. Peterson, 2008  
University of Wyoming, M.Sc., Zoology and Physiology, Statistics minor, James R. Lovvorn, 2003  
University of Michigan, B.Sc., Biology with Honors Thesis, Gerald R. Smith, 1999  
  
Editorships at peer-review journals in the field  
2013 - present Subject Matter Editor, PLOS ONE   
2011 – present Subject Matter Editor, Oikos   
  
Journal peer review  
Science; Proceedings of the Royal Society; Ecology Letters; Ecology; Ecography; Ecological Research; Oecologia; Oikos; Journal of Animal Ecology; PLOS ONE; Journal of Mammalogy; Animal Behavior; Journal of Wildlife Management; Wildlife Monographs; Current Anthropology.  
  
PROJECT MANAGER RESPONSIBILITIES:  
Dr. Joseph K. Bump will provide overall leadership, coordination, and oversight for each aspect of this project. Bump will be the primary advisor and mentor for postdoctoral research associate and co-advisor to field technicians supported by this project.   
  
ORGANIZATION DESCRIPTION:   
The Department of Fisheries, Wildlife, and Conservation Biology at the University of Minnesota Twin Cities provides world-class training and expertise to contribute to the management, conservation, and sustainable use of fisheries and wildlife resources.

**Organization:** U of MN - College of Food, Agricultural and Natural Resource Sciences

**Organization Description:**The Department of Fisheries, Wildlife, and Conservation Biology (FWCB) comprises a multidisciplinary group of scholars working on applied and fundamental problems related to the ecology of free-ranging wild animals, management of harvested and invasive species, and documentation and conservation of biodiversity. The mission of FWCB is to foster a high-quality natural environment by contributing to the management, protection, and sustainable use of fisheries and wildlife resources through teaching, research, and outreach. Our goals are to respond to societal needs for information and education pertaining to the conservation of our natural resources and to ensure excellent teaching, research, and outreach programs. Most of the research we pursue is intended to fill a critical gap in knowledge that will improve conservation and natural resource decisions.   
  
FWCB has a long tradition of public engagement. Our science is connected to Minnesota and the other locations in which we work around the world. FWCB is a hub of innovation for citizen science, which empowers people to formally contribute to conservation problem-solving. Our key citizen science programs, such as Minnesota Master Naturalists and Minnesota Aquatic Invasive Detectors, have statewide reach and impact. This project will have statewide impact as well.

## **Budget Summary**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Category / Name** | **Subcategory or Type** | **Description** | **Purpose** | **Gen. Ineli gible** | **% Bene fits** | **# FTE** | **Class ified Staff?** | **$ Amount** |
| **Personnel** |  |  |  |  |  |  |  |  |
| Principle Investigator |  | Responsible for overall project management and supervision of project post‐doctoral researcher. |  |  | 36.5% | 0.16 |  | $30,180 |
| Co-Principle Investigator and Project Postdoctoral Researcher |  | Leads data collection, management, and analyses required to achieve project Activities. Leads peer-reviewed manuscripts and professional presentations. Leads public outreach and broader impacts with media. |  |  | 25.4% | 2 |  | $150,480 |
| Extension Program Leader |  | Responsible for overall project management within the Minnesota Master Naturalist Program. |  |  | 36.5% | 0.1 |  | $11,226 |
| Extension Educator |  | Co-leads project Activities within the Minnesota Master Naturalist Program. |  |  | 36.5% | 0.1 |  | $10,508 |
| Extension Program Associate |  | Leads hunter recruitment, training, and coordination. Manages camera inventory and data acquisition. |  |  | 31.8% | 1.6 |  | $106,098 |
|  |  |  |  |  |  |  | **Sub Total** | **$308,492** |
| **Contracts and Services** |  |  |  |  |  |  |  |  |
| University of Minnesota Supercomputing Institute | Internal services or fees (uncommon) | The University of Minnesota Supercomputing Institute will provide high density data storage and backup for the hundreds of thousands of images and videos that project Activities will generate. The Institute will also provide data management consulting. |  |  |  | 0.02 |  | $4,400 |
|  |  |  |  |  |  |  | **Sub Total** | **$4,400** |
| **Equipment, Tools, and Supplies** |  |  |  |  |  |  |  |  |
|  | Equipment | 500 remote camera kits: camera, security case, cable lock, mount, batteries, memory cards @ $335 ea. | Needed to capture high definition images and video of wildlife at offal sites across Minnesota. |  |  |  |  | $167,500 |
|  | Equipment | 4 digital SLR camera kits: single lens reflex camera arrays with triggers, flashes, and 4K video capacity to generate high quality materials for outreach @ $6000 each. | Needed to generate 4K video for highest quality animal behavior interpretation and audio visual material for public outreach and social media. |  |  |  |  | $24,000 |
|  | Tools and Supplies | 10 external hard drives: 8TB drives that are portable @ $150 each | Mobil data storage capacity for field, lab, and office data maintenance and analysis. |  |  |  |  | $1,500 |
|  | Tools and Supplies | Postage fees | Needed to mail camera kits and memory cards to and from hunter volunteers to distribute supplies and collect data. |  |  |  |  | $1,800 |
|  |  |  |  |  |  |  | **Sub Total** | **$194,800** |
| **Capital Expenditures** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Acquisitions and Stewardship** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Travel In Minnesota** |  |  |  |  |  |  |  |  |
|  | Miles/ Meals/ Lodging | 1 vehicle rental for 2 years at 10,000 miles of travel @ $0.56 per mile = 5,600). | Needed for hunter recruitment, training, remote camera workshops & delivery, data recovery, public outreach, and project presentations. |  |  |  |  | $5,600 |
|  |  |  |  |  |  |  | **Sub Total** | **$5,600** |
| **Travel Outside Minnesota** |  |  |  |  |  |  |  |  |
|  | Conference Registration Miles/ Meals/ Lodging | Travel support for PI and Co-PI to attend one professional meeting each year for 2 years. | Needed for presentation of project methods, results, and implications at relevant professional meetings. For example, Annual meeting of The Wildlife Society. | X |  |  |  | $4,100 |
|  |  |  |  |  |  |  | **Sub Total** | **$4,100** |
| **Printing and Publication** |  |  |  |  |  |  |  |  |
|  | Publication | Publication page chargers for peer-reviewed journals: 3 per year @ $2000/article for 2 years | Needed to pay for publication of project related science articles |  |  |  |  | $12,000 |
|  | Printing | Hunter recruitment flyers and announcements in print media | Needed to broadly recruit hunters to participants in project Activities. |  |  |  |  | $1,608 |
|  |  |  |  |  |  |  | **Sub Total** | **$13,608** |
| **Other Expenses** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
|  |  |  |  |  |  |  | **Grand Total** | **$531,000** |

### **Classified Staff or Generally Ineligible Expenses**

|  |  |  |  |
| --- | --- | --- | --- |
| **Category/Name** | **Subcategory or Type** | **Description** | **Justification Ineligible Expense or Classified Staff Request** |
| **Travel Outside Minnesota** | Conference Registration Miles/Meals/Lodging | Travel support for PI and Co-PI to attend one professional meeting each year for 2 years. | Needed to disseminate project methods, results, and implications at relevant professional meetings that are held nationally. For example, Annual meeting of The Wildlife Society. This will broaden the impact of this project to a national audience and raise the profile of the ENRTF on the national stage. |

### **Non ENRTF Funds**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Category** | **Specific Source** | **Use** | **Status** | **Amount** |
| **State** |  |  |  |  |
| In-Kind | Un-recovered indirect costs (55% MTDC) | University of Minnesota resources used to support this project. | Secured | $290,000 |
|  |  |  | **State Sub Total** | **$290,000** |
| **Non-State** |  |  |  |  |
|  |  |  | **Non State Sub Total** | **-** |
|  |  |  | **Funds Total** | **$290,000** |

## **Attachments**

### **Required Attachments**

#### ***Visual Component***

File: [a5c7f446-b77.pdf](https://lccmrprojectmgmt.leg.mn/media/map/a5c7f446-b77.pdf)

#### ***Alternate Text for Visual Component***

This is a citizen-science project driven by hunters. We will recruit hunters statewide and provide remote cameras to deploy at field-dressed deer gut piles to study scavengers and hunter provisioning. The visual illustrates that this project will:  
- Advance knowledge about scavenger communities at hunter provided gut piles.  
- Better understand the potential for wildlife disease spread and contaminant exposure.  
- Statewide hunter participation across Minnesota biomes and human densities.  
- Man...

### **Optional Attachments**

#### ***Support Letter or Other***

|  |  |
| --- | --- |
| **Title** | **File** |
| UMN approval letter to submit | [afb76ce9-1c2.pdf](https://lccmrprojectmgmt.leg.mn/media/attachments/afb76ce9-1c2.pdf) |
| Letter of support and collaboration from Minnesota 4-H | [90e49005-562.pdf](https://lccmrprojectmgmt.leg.mn/media/attachments/90e49005-562.pdf) |
| Letter of support and collaboration from Back Country Hunters and Anglers | [0463ba4f-738.pdf](https://lccmrprojectmgmt.leg.mn/media/attachments/0463ba4f-738.pdf) |
| Letter of support and collaboration from Bluffland Whitetails Association | [ad0d5602-4ff.pdf](https://lccmrprojectmgmt.leg.mn/media/attachments/ad0d5602-4ff.pdf) |
| Letter of support and collaboration from Minnesota Dear Hunters Association (MDHA) | [86d01782-a2b.pdf](https://lccmrprojectmgmt.leg.mn/media/attachments/86d01782-a2b.pdf) |
| Letter of support and collaboration from Minnesota Center for Prion Research and Outreach (MNPRO) | [5802dac2-7e6.pdf](https://lccmrprojectmgmt.leg.mn/media/attachments/5802dac2-7e6.pdf) |

## **Administrative Use**

**Does your project include restoration or acquisition of land rights?**   
 No

**Does your project have potential for royalties, copyrights, patents, or sale of products and assets?**   
 No

**Do you understand and acknowledge IP and revenue-return and sharing requirements in 116P.10?**   
 N/A

**Do you wish to request reinvestment of any revenues into your project instead of returning revenue to the ENRTF?**   
 N/A

**Does your project include original, hypothesis-driven research?**   
 Yes

**Does the organization have a fiscal agent for this project?**   
 Yes, Sponsored Projects Administration