

**Environment and Natural Resources Trust Fund**

# 2022 Request for Proposal

## **General Information**

**Proposal ID:** 2022-262

**Proposal Title:** Above the Falls Regional Park Acquisition and Restoration

## **Project Manager Information**

**Name:** Adam Arvidson

**Organization:** Minneapolis Parks and Recreation Board

**Office Telephone:** (612) 230-6470

**Email:** aarvidson@minneapolisparks.org

## **Project Basic Information**

**Project Summary:** This project would acquire 3.25 acres of industrial land along the Mississippi River within the Above the Falls Regional Park.

**Funds Requested:** $950,000

**Proposed Project Completion:** December 31 2023

**LCCMR Funding Category:** Land Acquisition, Habitat, and Recreation (G)

## **Project Location**

**What is the best scale for describing where your work will take place?** Region(s): Metro

**What is the best scale to describe the area impacted by your work?** Region(s): Metro

**When will the work impact occur?** During the Project and In the Future

## **Narrative**

**Describe the opportunity or problem your proposal seeks to address. Include any relevant background information.**

All of the waterfront in Minneapolis has been public for more than 100 years—except the Mississippi River in North and Northeast Minneapolis. This historic gap in habitat and public access illuminates disparities across the city and creates a break in the Mississippi Flyway. Over years and with significant state assistance, parcels were purchased by MPRB and other public entities in the interest of implementing a grand park vision known as RiverFirst. That 2012 vision established a framework for Above the Falls Regional Park that would acquire and restore the entire riverfront, thereby closing historic access and habitat gaps.

On the west bank, nearly 3.5 miles of shoreline is in public hands and either is or will soon be converted to parkland with restored ecosystems. Stretching from near the Lowry Bridge northward to Interstate 694, this nearly continuous ribbon is comprised of Minneapolis’s Upper Harbor Terminal (soon to have public park on its shoreline), MPRB’s Northside Operations Center, and both the MPRB and Three Rivers Park District portions of North Mississippi Regional Park. It is only broken by a single parcel with 600 feet of shoreline. This project will close a small gap in this public riverfront.

**What is your proposed solution to the problem or opportunity discussed above? i.e. What are you seeking funding to do? You will be asked to expand on this in Activities and Milestones.**

Acquisition of this single parcel will create a continuous public shoreline and establish habitat connectivity along 3.5 miles of the Mississippi River—the most traveled flyway in the U.S. With assistance from the ENRTF, this gap can finally be closed. The timing is ideal: the Upper Harbor Terminal—thanks to state bond funding—will see the creation of naturalized park spaces within the next five years. This will extend the existing natural areas of North Mississippi Regional Park another mile to the south, if this single gap can be bridged. Acquisition of this parcel will benefit the entire flyway and make investment in communities that have been historically left without public water access.

We understand this acquisition would be eligible for ENRTF-funded Parks Acquisition Opportunity Funds through the Metropolitan Council, because it is a site with restoration potential within a regional park boundary. We are bringing a proposal directly to LCCMR because this acquisition could exhaust the PAOF quickly and, because of its urban/industrial character, it could be viewed as out of character with typical PAOF purchases. MPRB feels it is worthwhile to make this proposal directly so it can be discussed individually.

**What are the specific project outcomes as they relate to the public purpose of protection, conservation, preservation, and enhancement of the state’s natural resources?**

This project will help complete the continuous green ribbon of the Mississippi Flyway. To leave a 600 linear foot gap in the existing 3.5 miles of green would minimize the overall quality of the habitat and public access. The outcome of this project, therefore, is to contribute to the eventual acquisition of all the Minneapolis riverfront, as envisioned in plans that go back decades. Much work has been already completed to this end, and we are requesting funds to bridge the last gap.

## **Activities and Milestones**

### **Activity 1: Parcel Acquisition**

**Activity Budget:** $925,000

**Activity Description:**MPRB would work with its partners and the current property owner to acquire fee title to the parcel. MPRB staff time, legal costs, appraisals, and closing costs would be paid by MPRB as part of the grant match, with the entirety of the ENRTF funding going to actual parcel acquisition. A preliminary (restricted) appraisal has been performed but a new appraisal would be ordered upon receipt of funding.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Appraisal, Negotiations, and Due Diligence | November 30 2022 |
| Parcel Acquisition | April 30 2023 |

### **Activity 2: Restoration Planning**

**Activity Budget:** $25,000

**Activity Description:**MPRB will hire an ecological restoration professional through a competitive process and work with them to prepare a restoration plan for the site. The restoration plan will guide future restoration of the site. After completion of the restoration plan, MPRB will seek additional funding through a variety of sources to implement the restoration of the site, likely in conjunction with restoration activities on adjacent parcels.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Selection of Restoration Ecologist Professional | September 30 2022 |
| Completion of Restoration Plan | April 30 2023 |

## **Long-Term Implementation and Funding**

**Describe how the results will be implemented and how any ongoing effort will be funded. If not already addressed as part of the project, how will findings, results, and products developed be implemented after project completion? If additional work is needed, how will this be funded?**Long term maintenance and management of the parcel, including protection prior to restoration activities, will be performed by the Minneapolis Park and Recreation Board as part of its overall maintenance programs. Such activities do include paid staff work, volunteers, and partnerships with nonprofit organizations. MPRB will seek additional funding from a variety of sources to accomplish future restoration of the site.

## **Other ENRTF Appropriations Awarded in the Last Six Years**

|  |  |  |
| --- | --- | --- |
| **Name** | **Appropriation** | **Amount Awarded** |
| Invasive Carp Management Research in Lake Nokomis Subwatershed | M.L. 2016, Chp. 186, Sec. 2, Subd. 06g | $189,000 |
| Expanding Nature Knowledge and Experience with New Interactive Exhibits at North Mississippi Regional Park | M.L. 2018, Chp. 214, Art. 4, Sec. 2, Subd. 05h | $500,000 |

## **Project Manager and Organization Qualifications**

**Project Manager Name:** Adam Arvidson

**Job Title:** Director of Strategic Planning

**Provide description of the project manager’s qualifications to manage the proposed project.**Mr. Arvidson is MPRB’s Director of Strategic Planning, in which role he is responsible for large-scale planning of public lands. He is a registered landscape architect with 20+ years of experience in the public and private sector and has worked on numerous habitat and environment projects, including several funded through LCCMR and the Lessard-Sams Council. He is currently the project manager for the MPRB’s Ecological Systems Plan and is also leading the agency’s effort to create new environmentally sound master plans for each neighborhood park.

**Organization:** Minneapolis Parks and Recreation Board

**Organization Description:**With 179 park properties totaling nearly 6,800 acres of land and water, the Minneapolis Park and Recreation Board (MPRB) provides places and recreation opportunities for all people to gather, celebrate, contemplate, and engage in activities that promote health, well-being, community, and the environment. Each year, approximately 20 million visits are made to the nationally acclaimed Minneapolis park system. Its urban forests, natural areas, and waters endure and captivate. Its Grand Rounds National Scenic Byway, neighborhood parks, recreation centers, and diversified programming have made the Minneapolis park system an important component of what makes Minneapolis a great place to live, play and work.

## **Budget Summary**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Category / Name** | **Subcategory or Type** | **Description** | **Purpose** | **Gen. Ineli gible** | **% Bene fits** | **# FTE** | **Class ified Staff?** | **$ Amount** |
| **Personnel** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Contracts and Services** |  |  |  |  |  |  |  |  |
| Restoration Ecologist Professional to be determined | Professional or Technical Service Contract | The Restoration Ecologist Professional will prepare the restoration plan for the site, based on BWSR guidelines. |  |  |  | 0 |  | $25,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$25,000** |
| **Equipment, Tools, and Supplies** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Capital Expenditures** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Acquisitions and Stewardship** |  |  |  |  |  |  |  |  |
|  | Fee Title Acquisition | 3.25 Parcels: 1  |  |  |  |  |  | $925,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$925,000** |
| **Travel In Minnesota** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Travel Outside Minnesota** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Printing and Publication** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Other Expenses** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
|  |  |  |  |  |  |  | **Grand Total** | **$950,000** |

### **Classified Staff or Generally Ineligible Expenses**

|  |  |  |  |
| --- | --- | --- | --- |
| **Category/Name** | **Subcategory or Type** | **Description** | **Justification Ineligible Expense or Classified Staff Request** |

### **Non ENRTF Funds**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Category** | **Specific Source** | **Use** | **Status** | **Amount** |
| **State** |  |  |  |  |
|  |  |  | **State Sub Total** | **-** |
| **Non-State** |  |  |  |  |
| Cash | Minneapolis Park and Recreation Board General Fund as designated for general staffing and fringe. | Matching funds will be used for all personnel costs, including community engagement, landowner negotiation, and project administration for the acquisition and restoration activities. | Secured | $50,000 |
| Cash | Minneapolis Park and Recreation Board General Fund as designated for land acquisition. | Land acquisition designated funds will be used for all acquisition soft costs, as well as a portion of land costs. | Secured | $225,000 |
|  |  |  | **Non State Sub Total** | **$275,000** |
|  |  |  | **Funds Total** | **$275,000** |

## **Acquisition and Restoration**

### **Parcel List**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Name** | **County** | **Site Significance** | **Activity** | **Acres** | **Miles** | **Estimated Cost** | **Type of Landowner** | **Easement or Title Holder** | **Status of Work** |
| PID: 0302924310012 | Hennepin | The site has frontage on the Mississippi River but has been historically used for industrial uses. There is no intact ecosystem on the site. However, as part of Above the Falls Regional Park, this parcel would connect public lands and restored waterfront to the north (North Mississippi Regional Park) and the south (Upper Harbor Terminal) in an approximately 3.5-mile continuous public riverfront. | Fee Title | 3.25 | 0.11 | $1,150,000 | Private | Minneapolis Park and Recreation Board | Has not begun |
| **Totals** |  |  |  | **3.25** | **0.11** | **$1,150,000** |  |  |  |

### **Fee Acquisition**

**1. Describe the selection process for identifying and including proposed parcels on the parcel list, including an explanation of the criteria and decision-making process used to rank and prioritize parcels.**The extents of Above the Falls Regional Park were determined through extensive community engagement as part of the RiverFirst vision in 2011 and 2012. The boundary of this park is recognized by the Metropolitan Council and it includes both publicly owned and privately owned parcels. The ultimate vision is to acquire and bring into MPRB ownership all parcels within the boundary, including the one included in this request. Specific decisions around which parcels to acquire when is dependent on three main factors: willingness of the owner to sell, impact on completeness of the park, and available funding. This parcel is being brought forward because we understand the owner may have an interest in divesting the property and (as described in the project narrative) the positive impact on habitat and water access connectivity will be high. MPRB will be unable to acquire this parcel without outside assistance.

**2. List all adopted state, regional, or local natural resource plans in which the lands included in the parcel list are identified for the acquisition purposes you propose. Include the URL to the plan if one is available.**Though not strictly a natural resources plan, the MPRB- and City of Minneapolis-adopted RiverFirst Vision calls for the acquisition and restoration of this parcel, along with the entire riverfront in North and Northeast Minneapolis. The principles of RiverFirst are displayed in MPRB's Master Plan for Above the Falls Regional Park, which has been adopted by the Board of Commissioners and is pending at the Metropolitan Council. A link to the ATF Master Plan is found below.

https://www.minneapolisparks.org/park\_care\_\_improvements/park\_projects/current\_projects/above-the-falls-regional-park-master-plan-update/

**3. For any parcels acquired in fee title, a restoration and management plan must be prepared. Summarize the components and expected outcomes of restoration and management plans for parcels acquired by your organization, how these plans are kept on file by your organization, and overall strategies for long-term plan implementation, including how long-term maintenance and management needs of the parcel will be financed into the future.**Components of the restoration and management plan will include a description of current conditions, with a focus on hydrology, geology, and the aquatic biotic community as they apply large river systems; description of a target restoration community, which is most likely to be partly an aquatic to emergent wetland/riparian system and partly an upland grassland or savanna system; a timeline for restoration; and guidance for ongoing management of the restored areas. The restoration plan will be included in the creation of any future construction plans for the project and will guide both future construction and ongoing management. This plan will be kept both in MPRB staff project files and in the MPRB archive, as well as posted publicly on the MPRB website.

**4. For each parcel to be conveyed to a State of Minnesota entity (e.g., DNR) after purchase, provide a statement confirming that county board approval will be obtained.**Not applicable.

**5. If applicable (see M.S. 116P.17), provide a statement confirming that written approval from the DNR Commissioner will be obtained 10 business days prior to any final acquisition transaction.**MPRB confirms that M.S. 116P.17 will be followed and that written approval from the DNR Commissioner will be obtained.

## **Attachments**

### **Required Attachments**

#### ***Map***

File: [fa94f3bc-630.pdf](https://lccmrprojectmgmt.leg.mn/media/map/fa94f3bc-630.pdf)

#### ***Alternate Text for Map***

Map of North Minneapolis along the Mississippi River showing proposed acquisition parcel along with adjacent MPRB and City owned parcels....

#### ***Board Resolution or Letter***

|  |  |
| --- | --- |
| **Title** | **File** |
| Resolution 2020-175 authorizing submittal in previous year | [7e028a90-291.pdf](https://lccmrprojectmgmt.leg.mn/media/attachments/7e028a90-291.pdf) |

### **Optional Attachments**

#### ***Media Links***

|  |  |
| --- | --- |
| **Title** | **Link** |
| Above the Falls Master Plan | <https://www.minneapolisparks.org/park_care__improvements/park_projects/current_projects/above-the-falls-regional-park-master-plan-update/> |

## **Administrative Use**

**Does your project include restoration or acquisition of land rights?**
 Yes: Fee Acquisition,

**Does your project have potential for royalties, copyrights, patents, or sale of products and assets?**
 No

**Do you understand and acknowledge IP and revenue-return and sharing requirements in 116P.10?**
 N/A

**Do you wish to request reinvestment of any revenues into your project instead of returning revenue to the ENRTF?**
 N/A

**Does your project include original, hypothesis-driven research?**
 No

**Does the organization have a fiscal agent for this project?**
 No