

**Environment and Natural Resources Trust Fund**

# 2023 Request for Proposal

## **General Information**

**Proposal ID:** 2023-045

**Proposal Title:** MN River Valley State Trail, Appleton/Marsh Lake

## **Project Manager Information**

**Name:** Dawn Hegland

**Organization:** Swift County

**Office Telephone:** (320) 289-1981

**Email:** dawn.hegland@umvrdc.org

## **Project Basic Information**

**Project Summary:** This project will complete a critical Minnesota River State Trail connection to the recently redeveloped Marsh Lake Recreation area.

**Funds Requested:** $3,808,000

**Proposed Project Completion:** June 30, 2025

**LCCMR Funding Category:** Land Acquisition, Habitat, and Recreation (G)

## **Project Location**

**What is the best scale for describing where your work will take place?** Region(s): SW

**What is the best scale to describe the area impacted by your work?** Region(s): SW

**When will the work impact occur?** During the Project and In the Future

## **Narrative**

**Describe the opportunity or problem your proposal seeks to address. Include any relevant background information.**

Implementing the Appleton to Marsh Lake Trail segment of the Minnesota River State Trail has taken over 10 years. Legislative funding was initially provided to the DNR but initial corridors identified for trail alignment proved problematic due to land acquisition. A new alignment was identified in conjunction with the opportunity to connect to the Marsh Lake Ecosystem Restoration Project, a cooperative project between the Corps of Engineers, the DNR, and the Upper Minnesota River Watershed District to "restore the aquatic and riparian ecosystems within the Marsh Lake project area, which is along the Minnesota River and within the Lac qui Parle Wildlife Management Area (WMA) boundary. Marsh Lake is a 5,000 acre shallow reservoir along the Minnesota River in Big Stone, Chippewa, Lac qui Parle, and Swift Counties."

Due to the length of time to develop and secure funding for the Marsh Lake project and the impact to the trail corridor and connection points, the DNR worked cooperatively with Swift County to retain funding for the trail until the Marsh Lake Project was completed in 2021. Swift County is currently soliciting bids for the construction of the first segment of a trail to connect to the Marsh Lake project.

**What is your proposed solution to the problem or opportunity discussed above? Introduce us to the work you are seeking funding to do. You will be asked to expand on this proposed solution in Activities & Milestones.**

This proposal will complete the final 3 miles of a Minnesota River State Trail segment, and a necessary bridge, of a trail between Appleton and the Marsh Lake recreation area. The first 2 miles of this trail is being constructed through a partnership between Swift County and the DNR.

**What are the specific project outcomes as they relate to the public purpose of protection, conservation, preservation, and enhancement of the state’s natural resources?**

This trail will provide a recreation enhancement to the Marsh Lake area and a critical segment of the Minnesota River state Trail corridor.

## **Activities and Milestones**

### **Activity 1: Design and engineering**

**Activity Budget:** $480,000

**Activity Description:**Design trail and bridge specifications

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Trail Design Completed | March 31, 2024 |
| Environmental Review | June 30, 2024 |
| Bid speciifcations | September 30, 2024 |

### **Activity 2: Construction**

**Activity Budget:** $3,200,000

**Activity Description:**Construction of trail and bridge

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| Bid award | November 30, 2024 |
| Construction | June 30, 2025 |

### **Activity 3: Project Administration**

**Activity Budget:** $128,000

**Activity Description:**Swift County will manage and oversee the design/engineering and construction of this project using county employees.

**Activity Milestones:**

|  |  |
| --- | --- |
| **Description** | **Completion Date** |
| procure design/engineering services | September 30, 2023 |
| Oversee design/engineering and construction | June 30, 2025 |

## **Project Partners and Collaborators**

|  |  |  |  |
| --- | --- | --- | --- |
| **Name** | **Organization** | **Role** | **Receiving Funds** |
| Kent Skaar | MN DNR | The DNR has led and developed all preliminary planning for the proposed trail segments and would remain a critical partner and participant in the successful completion of the project. | No |
| Andy Sander | Swift County | As county engineer Andy has worked with the DNR to manage the design, engineering and construction of the phase 1 portion of this trail corridor. The County will also oversee the design engineering and construction of this proposed phase. | Yes |

## **Long-Term Implementation and Funding**

**Describe how the results will be implemented and how any ongoing effort will be funded. If not already addressed as part of the project, how will findings, results, and products developed be implemented after project completion? If additional work is needed, how will this work be funded?**Swift County has been a strong and willing partner with the DNR to implement this segment of the Mn River State Trail. Swift County has spent internal resources on staffing and administration of the first phase of this project and would expect to allocate or seek any additional resources needed to complete this project.

## **Project Manager and Organization Qualifications**

**Project Manager Name:** Dawn Hegland

**Job Title:** Executive Director

**Provide description of the project manager’s qualifications to manage the proposed project.**The UMVRDC provides technical consulting services to counties and cities. The UMVRDC has a long standing relation with the planning and development of the Minnesota River Valley State Trail corridor and this specific trail segment. The UMVRDC has expertise in grant management and administration of state and federal funding for a wide variety of project types including recreation improvements.

**Organization:** Swift County

**Organization Description:**Swift County is a county in western Minnesota.

## **Budget Summary**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Category / Name** | **Subcategory or Type** | **Description** | **Purpose** | **Gen. Ineli gible** | **% Bene fits** | **# FTE** | **Class ified Staff?** | **$ Amount** |
| **Personnel** |  |  |  |  |  |  |  |  |
| County Engineer |  | Oversee the design, engineering and construction of the project. |  |  | 25% | 0.5 |  | $128,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$128,000** |
| **Contracts and Services** |  |  |  |  |  |  |  |  |
| TBD | Professional or Technical Service Contract | Design and engineering |  |  |  | 5 |  | $480,000 |
| TBD | Professional or Technical Service Contract | Construction of trail and bridge |  |  |  | - |  | $3,200,000 |
|  |  |  |  |  |  |  | **Sub Total** | **$3,680,000** |
| **Equipment, Tools, and Supplies** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Capital Expenditures** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Acquisitions and Stewardship** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Travel In Minnesota** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Travel Outside Minnesota** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Printing and Publication** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
| **Other Expenses** |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | **Sub Total** | **-** |
|  |  |  |  |  |  |  | **Grand Total** | **$3,808,000** |

### **Classified Staff or Generally Ineligible Expenses**

|  |  |  |  |
| --- | --- | --- | --- |
| **Category/Name** | **Subcategory or Type** | **Description** | **Justification Ineligible Expense or Classified Staff Request** |

### **Non ENRTF Funds**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Category** | **Specific Source** | **Use** | **Status** | **Amount** |
| **State** |  |  |  |  |
|  |  |  | **State Sub Total** | **-** |
| **Non-State** |  |  |  |  |
|  |  |  | **Non State Sub Total** | **-** |
|  |  |  | **Funds Total** | **-** |

## **Attachments**

### **Required Attachments**

#### ***Visual Component***

File: [05d07bd2-a22.pdf](https://lccmrprojectmgmt.leg.mn/media/map/05d07bd2-a22.pdf)

#### ***Alternate Text for Visual Component***

Map of the trail corridor showing Phase 1 ( currently out for bids) and the proposed phase 2 connection to the Marsh Lake Dam area...

#### ***Board Resolution or Letter***

|  |  |
| --- | --- |
| **Title** | **File** |
| Swift County Resolution | [0ef90c2f-0fe.pdf](https://lccmrprojectmgmt.leg.mn/media/attachments/0ef90c2f-0fe.pdf) |

## **Administrative Use**

**Does your project include restoration or acquisition of land rights?**
 No

**Does your project have potential for royalties, copyrights, patents, or sale of products and assets?**
 No

**Do you understand and acknowledge IP and revenue-return and sharing requirements in 116P.10?**
 N/A

**Do you wish to request reinvestment of any revenues into your project instead of returning revenue to the ENRTF?**
 N/A

**Does your project include original, hypothesis-driven research?**
 No

**Does the organization have a fiscal agent for this project?**
 No